# Common Market for Eastern and

# Southern Africa (COMESA)

# Great Lakes Trade Facilitation Project (GLTFP)

# Financial statements

# for the year ended 31 December 2017

# COMESA - Great Lakes Trade Facilitation Project

# Financial statements

# for the year ended 31 December 2017

Contents	Page

Project implementation report	1 – 3

Statement of responsibility in respect of the preparation of financial statements                    	 4

Independent auditor’s report	5 - 7

Statement of financial position	8

Statement of income and expenditure 	9

Statement of cash flows	10

Notes to the financial Statements	11 - 17

Appendix I – Comparison of actual to budgeted expenditure	18 – 22

Appendix II – Schedule of fixed assets	23 – 26

# COMESA - Great Lakes Trade Facilitation Project (GLTFP)

Project implementation report

for the year ended 31 December 2017

- Introduction

The International Development Association (IDA), an agency of the World Bank Group and the Common Market for Eastern and Southern Africa (COMESA) signed a Financing Agreement on 19th November 2015 for a grant to the amount of Special Drawing Rights (DSR) – 3.6 million (US Dollar- 5 million equivalent) to facilitate implementation of the Great Lakes Trade Facilitation Project (GLTFP) over a period of five years.

The rationale of the project is to facilitate cross-border trade by increasing the capacity for commerce and reducing the costs faced by traders, especially small-scale and women traders, at targeted borderland locations in Democratic Republic of Congo (DRC), Uganda and Rwanda. The project supports regional peace and stability through programs to improve livelihoods in border areas, promote cross-border trade, and strengthen economic interdependence.

The beneficiaries of the COMESA components of the GLTFP will primarily be cross-border traders, especially women, and border agency officials. Vulnerable families in borderland areas will be secondary beneficiaries as incomes of cross-border traders’ increase. The government of DRC, Uganda and Rwanda will also be secondary beneficiaries through increased revenue collection of trade taxes, the benefits of which should filter down to the general populations of these countries.

The project will benefit COMESA through implementing regulations and procedures for the treatment of small-scale border traders, such as a toll-free complaint hotline, simplified immigration and health-related procedures, streamlined access to airfreight and duty-free entry for eligible goods.

- Objectives of the project

The Project objective is to facilitate cross-border trade by increasing the capacity for commerce and reducing the costs faced by traders, especially small-scale and women traders, at targeted locations in the borderlands. The total project amount is USD79 million distributed as follows: Rwanda USD 34 million (loan), DR Congo USD 30 million (loan), Uganda USD 10 million (loan) and Secretariat $5 million (grant). The project consists of four components. Two of the components will be executed at the national level while others will be executed at the regional level to provide for sharing experiences and best practices.

Key components of the project include:

- Improving core trade infrastructure and facilities in the border areas

- Implementation of policy and procedural reforms and capacity building to facilitate cross-border trade in goods and services;

- Performance based management in cross border administration; and

- Implementation support, communication, monitoring and evaluation.

# COMESA - Great Lakes Trade Facilitation Project (GLTFP)

Project implementation report (continued)

for the year ended 31 December 2017

- Project implementation status

During the period under review the Secretariat focused on the implementation of the approved work plan of the year.

In order to facilitate the smooth running of the project, staff of the project implementation unit (PIU) namely a Procurement Expert, a Project Accountant and a Regional Trade Information Desk Officer were recruited. Together with the Project Coordinator, the total staff of the PIU is now four.

The project also proceeded with the operationalization of the Trade Information Desks. In total, eighteen Trade Information Desk Officers (TIDOs) were recruited to work at nine project border posts in DR Congo, Rwanda and Uganda. Office furniture, office equipment and stationery were purchased and sent to the TIDOs office at border posts. To enhance the capacity of the TIDOs in the delivery of their responsibilities and also to support the dissemination and application of the COMESA Regulations and Simplified Trade Regime, two training workshops were conducted in June and November 2017 respectively.

As the project is also involve in the implementation of COMESA Simplified Trade Regime (STR), an STR Consultant was hired   under the project in 2017 to assist. In order to provide a platform for sharing of information by various stakeholders in the implementation of the COMESA Simplified Trade Regime, a Regional Dialogue was organized in September 2017 where stakeholders from Rwanda, DR Congo and Uganda met and discussed. An STR training and awareness workshop was also conducted at all the ten project border posts in December 2017 to enhance the technical capabilities and skills of agents working at the borders. A total number of 400 border officials and traders participated in the workshop.

Another major activity undertaken during the period was holding of the project border assessment mission by a team of staff from the Secretariat.  The team visited all project borders and carried out an assessment of project infrastructure needs (such as office space), communication needs and other needs related to the gender aspects of the project.  The team also held consultations with local actors from government, civil society, Cross-Border Trade Associations in order to explore potential for partnerships in implementation of the various project activities, and to identify policy issues that need to be addressed for smooth implementation of the project.

The hire of consultants for the development of Training of Trainers Manual and development of project communication and advocacy strategy are in progress. Their contract was finalized in January 2018.

In 2017, disbursement to the total amount of US$ 817,461 (2016: US$ 371,950) was made by World Bank Group in July 2017. As at 31 December 2017, a total amount of US$ 790,160 (2016: US$ 75,940) was spent to undertake planned activities which represent an expenditure rate of 49.6% (2016: 20%) of budgeted expenditure.

- Prospects

In order to meet the core objective of the project which is to facilitate cross border trade at targeted borderland locations in DR Congo, Uganda and Rwanda, the following activities will be implemented in the next financial year:

  - Finalisation of training of trainer’s manual and training of officials from project Member States;

# COMESA - Great Lakes Trade Facilitation Project (GLTFP)

Project implementation report (continued)

for the year ended 31 December 2017

- Prospects (continued)

  - Finalisation of GLTFP Communication and Advocacy Strategy in order to ensure coordination and communication of COMESA Simplified Trade Regime ( STR) to cross border traders  and implementation of recommendations of the strategy which will assist in greater visibility of the project;

  - Finalisation of the development of GLTFP website and its maintenance. The website will assist in  the dissemination of information to public;

  - Recruitment of a part time Monitoring & Evaluation Expert so as to assist in building the capacity of government agencies to capture progress in improving conditions for cross border trade;

  - Facilitate bilateral meetings between the project Member States so as to formalize and institutionalise cross-border collaboration platforms for information sharing and troubleshooting.

  - GLTFP will continue to enhance the technical capacities and skills of agent working at the border, supporting improved governance, reduced levels of harassment and more efficient control and processing of goods and people by   continuing to conduct comprehensive training programme at the project border posts.

- Program management team

The management team at the COMESA Secretariat is comprised of the following:

Sindiso Ngwenya 			Secretary General

Ambassador Kipyego Cheluget		Assistant Secretary General (Programmes)

Clement Kanyama			Director – Budget and Finance

Dr. Francis Mangeni			Director – Trade

Martha Elimu				Acting Director – Human Resources & Administration

Thomas Barasa				Project Coordinator

# Sindiso Ngwenya

Date:……….June 2018

COMESA - Great Lakes Trade Facilitation Project (GLTFP)

Statement of responsibility in respect of the preparation of financial statements

In accordance with the COMESA financial rules and regulations, the Secretary General is responsible for the preparation and fair presentation of the COMESA - Great Lakes Trade Facilitation Project Financial Statements, comprising the statement of financial position as at 31 December 2017, statements of income and expenditure and cash flows for the year then ended, and the notes to the financial statements, which include a summary of significant accounting policies and other explanatory notes, in accordance with  the basis of accounting described in note 2, the requirements of the COMESA financial rules and regulations and the Protocol of agreement between COMESA and the World Bank Group.

The Secretary General is also responsible for such internal control as he determines are necessary to enable the preparation of financial statements that are free from material misstatement whether due to fraud or error and for maintaining adequate accounting records and an effective system of risk management as well as the preparation of supplementary schedules included in these financial statements.

The Secretary General has made an assessment of the COMESA - Great Lakes Trade Facilitation Project’s ability to continue as a going concern and has no reason to believe the Project will not be a going concern in the year ahead.

The auditor is responsible for reporting on whether the financial statements are fairly presented in accordance with the applicable financial reporting framework.

Approval of the Financial Statements

The financial statements of COMESA - Great Lakes Trade Facilitation Project, as identified in the first paragraph, were approved by the Secretary General on ………June 2018 and are signed by:

_______________________

Sindiso Ngwenya

Secretary General

Independent auditor’s report

To the members of COMESA - Great Lakes Trade Facilitation Project

Report on the audit of the financial statements

Opinion

We have audited the financial statements of COMESA – Great Lakes Trade Facilitation Project (“the Project”), which comprise the statement of financial position as at 31 December 2017, the statements of income and expenditure and cash flows for the year then ended, and notes to the financial statements, including a summary of significant accounting policies and other explanatory information as set out on pages 8 to 17.

In our opinion, the financial statements present fairly, in all material respects, the financial position of COMESA – Great Lakes Trade Facilitation Project as at 31 December 2017 and its financial performance and cash flows for the year then ended in accordance with the basis of accounting described in note 2, and the requirements of the COMESA financial rules and regulations and the Protocol of agreement between COMESA and the World Bank.

Basis for opinion

We conducted our audit in accordance with International Standards on Auditing (ISAs). Our responsibilities under those standards are further described in the Auditors’ Responsibilities for the Audit of the Financial Statements section of our report. We are independent of the Project in accordance with the International Ethics Standards Board for Accountants' Code of Ethics for Professional Accountants (IESBA Code), and we have fulfilled our other ethical responsibilities in accordance with the IESBA Code. We believe that the audit evidence we have obtained is sufficient and appropriate to provide a basis for our opinion.

Basis of Accounting and Restriction of Use and Distribution

We draw attention to note 2 to the financial statements, which describes the basis of accounting. The financial statements are prepared to assist the Project to comply with the financial reporting requirements referred to above. As a result, the financial statements may not be suitable for another purpose. Our report is intended solely for the Project and should not be used by or distributed to parties other than the Project. Our opinion is not modified in respect of this matter.

Other information

The Secretary General is responsible for the other information. The other information comprises the Project Implementation Report, the statement of responsibility in respect of the preparation of financial statements and supplementary information set out on pages 18 - 26. The other information does not include the financial statements and opinion thereon.

Our opinion on the financial statements does not cover the other information and we do not express an audit opinion or any form of assurance conclusion thereon.

In connection with our audit of the financial statements, our responsibility is to read the other information and, in doing so, consider whether the other information is materially inconsistent with the financial statements or our knowledge obtained in the audit, or otherwise appears to be materially misstated. If, based on the work we have performed, we conclude that there is a material misstatement of this other information, we are required to report that fact. We have nothing to report in this regard.

ABCD

Responsibilities of the Secretary General for the financial statements

The Secretary General is responsible for the preparation and fair presentation of the financial statements in accordance with  the basis of accounting described in note 2, the requirements of the COMESA financial rules and regulations and the Protocol of agreement between COMESA and the World Bank, and for such internal control as the Secretary General determines is necessary to enable the preparation of financial statements that are free from material misstatement, whether due to fraud or error.

Responsibilities of the Secretary General for the financial statements (continued)

In preparing the financial statements, the Secretary General is responsible for assessing the Project’s ability to continue as a going concern, disclosing, as applicable, matters related to going concern and using the going concern basis of accounting unless the Secretary General either intends to liquidate the Project or to cease operations, or has no realistic alternative but to do so.

Auditors’ Responsibilities for the Audit of the Financial Statements

Our objectives are to obtain reasonable assurance about whether the financial statements as a whole are free from material misstatement, whether due to fraud or error, and to issue an auditors’ report that includes our opinion. Reasonable assurance is a high level of assurance, but is not a guarantee that an audit conducted in accordance with ISAs will always detect a material misstatement when it exists. Misstatements can arise from fraud or error and are considered material if, individually or in the aggregate, they could reasonably be expected to influence the economic decisions of users taken on the basis of these financial statements.

As part of an audit in accordance with ISAs, we exercise professional judgment and maintain professional scepticism throughout the audit. We also:

- Identify and assess the risks of material misstatement of the financial statements, whether due to fraud or error, design and perform audit procedures responsive to those risks, and obtain audit evidence that is sufficient and appropriate to provide a basis for our opinion. The risk of not detecting a material misstatement resulting from fraud is higher than for one resulting from error, as fraud may involve collusion, forgery, intentional omissions, misrepresentations, or the override of internal control.

- Obtain an understanding of internal control relevant to the audit in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the Project’s internal control.

- Evaluate the appropriateness of accounting policies used and the reasonableness of accounting estimates and related disclosures made by management.

- Conclude on the appropriateness of management’s use of the going concern basis of accounting and, based on the audit evidence obtained, whether a material uncertainty exists related to events or conditions that may cast significant doubt on the Project’s ability to continue as a going concern. If we conclude that a material uncertainty exists, we are required to draw attention in our auditors’ report to the related disclosures in the financial statements or, if such disclosures are inadequate, to modify our opinion. Our conclusions are based on the audit evidence obtained up to the date of our auditors’ report. However, future events or conditions may cause the Project to cease to continue as a going concern.

- Evaluate the overall presentation, structure and content of the financial statements, including the disclosures, and whether the financial statements represent the underlying transactions and events in a manner that achieves fair presentation.

ABCD

We communicate with those charged with governance regarding, among other matters, the planned scope and timing of the audit and significant audit findings, including any significant deficiencies in internal control that we identify during our audit.

KPMG Chartered Accountants                                                                                       ………June 2018

Cheelo Hamuwele                                                                             		             AUD/F001044

Audit principal

# COMESA - Great Lakes Trade Facilitation Project (GLTFP)

Statement of financial position

for the year ended 31 December 2017

In United States Dollars

|  | Note | 2017 |  | 2016 |
| --- | --- | --- | --- | --- |
| Assets |  |  |  |  |
| Current assets |  |  |  |  |
| Cash and cash equivalents | 11 | 282,512 |  | 306,963 |
| Receivables | 12 | 49,395 |  | 15,450 |
| Total assets |  | 331,907 |  | 322,413 |
| Liabilities |  |  |  |  |
| Current liabilities |  |  |  |  |
| Payables | 13 | 8,596 |  | 26,403 |
| Deferred income | 14 | 323,311 |  | 296,010 |
| Total funds and liabilities |  | 331,907 |  | 322,413 |

The Financial Statements were approved by the Secretary General on ……………June 2018 and signed by:

...............................................

Secretary General

The notes on pages 11 to 17 are an integral part of these financial statements.

# COMESA - Great Lakes Trade Facilitation Project

Statement of income and expenditure

for the year ended 31 December 2017

In United States Dollars

|  | Note | 12 months to 31 Dec 2017 |  | 6 months to 31 Dec 2016 |
| --- | --- | --- | --- | --- |
| Income |  |  |  |  |
| Deferred Income released to income | 14 | 790,160 |  | 75,940 |
| Programme expenditure |  |  |  |  |
| Salaries |  | 282,199 |  | 8,500 |
| Staff costs – repatriation |  | 12,307 |  | - |
| Airfares |  | 62,078 |  | 14,006 |
| Daily subsistence allowance (DSA) |  | 179,395 |  | 36,660 |
| Translation fees |  | 4,716 |  | 147 |
| Interpretation fees |  | 25,546 |  | 2,240 |
| Meetings & workshops |  | 85,334 |  | 1,139 |
| Scanner |  | - |  | 293 |
| Office equipment |  | 24,189 |  | 2,581 |
| Computer equipment |  | 46,826 |  | 10,004 |
| Bank Charges |  | 4,926 |  | 370 |
| Audit Fee |  | 1,000 |  | - |
| Printing and stationery |  | 3,828 |  | - |
| Office Supplies |  | 26,022 |  | - |
| Consultancy fees |  | 27,451 |  | - |
| Training costs |  | 3,493 |  | - |
| Advertisement |  | 850 |  | - |
| Total expenditure | 10 | 790,160 |  | 75,940 |
| Surplus of income over expenditure for the year |  | - |  | - |

The notes on pages 11 to 17 are an integral part of these financial statements.

# COMESA - Great Lakes Trade Facilitation Project

Statement of cash flows

for the year ended 31 December 2017

In United States Dollars

|  | Note | 12 months to 31 Dec 2017 |  | 6 months to 31 Dec 2016 |
| --- | --- | --- | --- | --- |
| Cash flows from operating activities |  |  |  |  |
| Deferred Income released to income | 10 | (790,160) |  | (75,940) |
| Changes in: |  |  |  |  |
| Receivables | 12 | (33,945) |  | ( (15,450) |
| Payables | 13 | (17,807) |  | 26,403 |
| Net cash used in operating activities |  | (841,912) |  | (64,987) |
| Cash flow from financing activities |  |  |  |  |
| Grants received | 8 | 817,461 |  | 371,950 |
| Net cash from financing activities |  | 817,461 |  | 371,950 |
| Net (decrease)/increase in cash and cash equivalents |  | (24,451) |  | 306,963 |
| Cash and cash equivalents at 1 January 2017 | 11 | 306,963 |  | - |
| Cash and cash equivalents at 31 December 2017 | 11 | 282,512 |  | 306,963 |

The notes on pages 11 to 17 are an integral part of these financial statements.

# COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements

for the year ended 31 December 2017

1	Reporting project

The International Development Association (IDA), an agency of the World Bank Group and the Common Market for Eastern and Southern Africa (COMESA) signed a Financing Agreement on 19th November 2015 for a grant to the amount of Special Drawing Rights (SDR)-3.6 million (US Dollar - 5 million equivalent) to facilitate implementation of Great Lakes Trade Facilitation Project (GLTFP) over a period of five years. The rationale of the project is to facilitate cross-border trade by increasing the capacity for commerce and reducing the costs faced by traders, specifically small-scale and women traders, at targeted borderland locations in Democratic Republic of Congo (DRC), Uganda and Rwanda. The project will benefit COMESA through implementing regulations and procedures for the treatment of small scale border traders such as a toll-free hotline, simplified immigration and health related procedures, streamlined access to airfreight and duty-free entry for eligible goods. The COMESA -Great Lakes Trade Facilitation Project (GLTFP) is domiciled in Zambia. The address of the registered office is COMESA Secretariat, Ben Bella Road, P. O Box 30051, Lusaka, Zambia.

2	Basis of accounting

These financial statements have been prepared on a modified cash basis in accordance with the requirements of the COMESA rules and regulations and the Protocol of agreement between COMESA and the World Bank Group.

3	Going concern

The financial statements have been prepared on a going concern basis and accounting policies have been applied consistently throughout the year under review.

4	Functional and presentation currency

These financial statements are presented in United States Dollar (USD) as required by the Protocol of agreement between COMESA and the World Bank Group.

5	Use of estimates and judgements

There were no estimates or judgements in the preparation of the financial statements.

6	Reporting date

The Great Lakes Trade Facilitation Project started its operations in July 2016 and the set of Financial Statements presented for 31 December 2017 is the second report to be audited for the Project.

# COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements (continued)

for the year ended 31 December 2017

In United States Dollars.

7	Measurement base

The accounting principles recognised as appropriate for the measurement and reporting of the financial performance, cash flows, and financial position is on an accrual basis and using historical cost in the preparation of the financial statements.

8	Income

|  |  | 12 months to 31 Dec 2017 |  | 6 months to 31 Dec 2016 |
| --- | --- | --- | --- | --- |
| Disbursement by World Bank Group |  | 817,461 |  | 371,950 |

Disbursement for the amount of US$ 817,461 was effected by the World Bank in July 2017 for implementation of planned activities as per approved operational plan.

9	Other income

|  |  | 12 months to 31 Dec 2017 |  | 6 months to 31 Dec 2016 |
| --- | --- | --- | --- | --- |
| Other income |  | - |  | - |

The GLTFP does not have any other income for the year under review.

10	Programme expenditure

|  | 12 months to 31 Dec 2017 |  | 6 months to 31 Dec 2016 |
| --- | --- | --- | --- |
| Staff costs-salaries Staff costs- Repatriation cost | 282,199 12,307 |  | 8,500 - |
| Other expenses – transport, subsistence, conferences and office supplies | 495,654 |  | 67,440 |
| Total | 790,160 |  | 75,940 |

Staff emoluments pertain to payment of salary for staff namely the project implementation unit at the COMESA Secretariat and Trade Information Desk Officers (TIDOs) at the project border posts. The GLTFP staff comprise of 4 staff for the project implementation unit and 18 TIDOs stationed at 9 border posts. Other expenses which pertain to operating expenses, capital expenditure and programme expenditure which were incurred for implementation of planned activities.

11	Cash and cash equivalents

|  |  | 2017 |  | 2016 |
| --- | --- | --- | --- | --- |
| Cash at bank- Citi Bank US $ Account |  | 282,512 |  | 306,964 |

12	Receivables

| Imprest |  | 26,500 |  | 15,450 |
| --- | --- | --- | --- | --- |
| Other receivables |  | 22,895 |  | - |
| Total |  | 49,395 |  | 15,450 |

Imprest was for servicing of STR Training and Awareness Workshop conducted in December 2017. Retirement was done in January 2018. Other receivables pertain to amount debited in error by the Bank relating to another COMESA project from the GLTFP bank account during the year. This error was rectified through a refund to the GLTFP bank account in January 2018 by the Bank.

# COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements (continued)

for the year ended 31 December 2017

In United States Dollars.

13	Payables

|  | 2017 |  | 2016 |
| --- | --- | --- | --- |
| Kenya Airways | 3,528 |  | 13,379 |
| Reliance Technologies | - |  | 6,078 |
| Microsource | - |  | 4,600 |
| Ms Martha Mutesayire | - |  | 147 |
| MFI Digital Solutions | - |  | 2,199 |
| STR Consultant – Paul Bagabo | 5,068 |  | - |
|  | 8,596 |  | 26,403 |

Payables pertain to expenditure for air fares and STR consultancy fee which was due in 2017 but payments effected only in 2018.

14	Deferred income

|  | 12 months to 31 Dec 2017 |  | 6 months to 31 Dec 2016 |
| --- | --- | --- | --- |
| Balance 1 January | 296,010 |  | - |
| Grant received from World Bank | 817,461 |  | 371,950 |
| Deferred income released to income | (790,160) |  | (75,940) |
| Balance 31 December | 323,311 |  | 296,010 |

The amount relates to unspent grant for the year under review from disbursement made by World Bank Group in 2017 and also unspent amount carried forward from 2016. This amount will be carried forward to be used in next financial year.

14.1	Deferred income reconciled to cash and cash equivalents

|  | Note | 2017 |  | 2016 |
| --- | --- | --- | --- | --- |
| Cash and cash equivalents | 11 | 282,512 |  | 306,963 |
| Charged to fund – Unpaid from bank | 13 | (8,596) |  | (26,403) |
| Paid from Bank – Unallocated to project expenditure | 12 | 49,395 |  | 15,450 |
| Deferred income | 14 | 323,311 |  | 296,010 |

COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements (continued)

for the year ended 31 December 2017

In United States Dollars.

14.2	Undrawn funds from World Bank Group

|  |  |  | 2017 |  | 2016 |
| --- | --- | --- | --- | --- | --- |
| Grant as per Financing Agreement |  |  | 5,000,000 |  | 5,000,000 |
| Cash drawn to date |  |  | (1,189,411) |  | (371,950) |
| Available at 31 December |  |  | 3,810,589 |  | 4,628,050 |

14.3	Assets: Analysis of cash received from World Bank Group as at 31 December 2017

|  |  |  | 2017 |  | 2016 |
| --- | --- | --- | --- | --- | --- |
| Cash and cash equivalents |  | 11 | 282,512 |  | 306,963 |
| Cumulative expenditure recognised to date |  |  | 866,100 |  | 75,940 |
| Amount payable to third parties |  | 13 | (8,596) |  | (26,403) |
| Amount receivable from third parties |  | 12 | 49,395 |  | 15,450 |
| Cumulative grant received to date |  |  | 1,189,411 |  | 371,950 |

14.4	Deferred income analysis of cash received from World Bank Group

|  |  |  | 2017 |  | 2016 |
| --- | --- | --- | --- | --- | --- |
| Deferred income – Fund as at 31 December |  |  | 323,311 |  | 296,010 |
| Income recognised to date |  |  | 866,100 |  | 75,940 |
| Cumulative grant received to date |  |  | 1,189,411 |  | 371,950 |

15 	Contingent liabilities

There were no contingent liabilities as at 31 December 2017 (2016: Nil).

16	Subsequent events

There were no subsequent events requiring disclosure or adjustments to these financial statements.

# COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements (continued)

for the year ended 31 December 2017

In United States Dollars.

17	Significant accounting policies

The accounting policies set out below have been applied consistently to all periods presented in these Financial Statements.

Set out below is an index of significant accounting policies, the details of which are available on the pages that follow:

- Income recognition

- Deferred income

- Expenditure

- Income tax

- Financial instruments

- Foreign currency

- Income recognition

Grants are recognised where there is reasonable assurance that the grant will be received and all attached conditions will be complied with. When the grant relates to an expense item, it is recognised as income on a systematic basis over the periods that the related costs, for which it is intended to compensate, are expensed. When the grant relates to an asset, it is recognised as income in equal amounts over the expected useful life of the related asset.

- Deferred income

Deferred income are grants received from African Development Bank which have not been utilised in the period. Income is only recognised when related expenditure for which the grant was obtained has been incurred.

(c)	Expenditure

Project expenditure is recorded when all the necessary conditions for the grant with regard to expenditure are met or when there is reasonable assurance that the project will comply with the conditions attaching to the grant with regard to expenditure.

(d)	Income tax

The project is exempt from income tax under paragraph 4b of Part II of Second Schedule to the Income Tax Act 1966 (as amended), Cap 323 of Laws of Zambia.

# COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements (continued)

for the year ended 31 December 2017

In United States Dollars.

17	Significant accounting policies (continued)

(e)	Financial instruments

A financial instrument is any contract that gives rise to a financial asset of one entity and a financial liability or equity instrument of another entity.

- Financial assets

Cash and cash equivalents

Cash and cash equivalents are defined as cash on hand, demand deposits and short-term, highly liquid investments readily convertible to known amounts of cash and subject to insignificant risk of changes in value.

Cash on hand and on call is carried at fair value. Deposits held on call are classified as loans originated by the Project and carried at amortised cost. Due to the short term nature of these, the amortised cost approximates its fair value.

Other receivables

Receivables are non-derivative financial assets with fixed or determinable payments that are not quoted in an active market.  Other receivables, which generally have 30 day terms, are recognised and carried at original invoice amount less an allowance for any uncollectible amounts as the effect of imputing interest is considered to be insignificant.

In relation to other receivables, a provision for impairment is made when there is objective evidence (such as significant financial difficulties of the debtor) that the Project will not be able to collect all of the amounts due under the original terms of the invoice. The carrying amount of the receivable is reduced through use of an allowance account. Impaired debts are derecognised when they are assessed as uncollectible.

- Financial liabilities

Other payables

Other payables are subsequently measured at amortised cost using the effective interest method. The effective interest method is a method of calculating the amortised cost of a financial liability and of allocating interest expense over the relevant period. The effective interest rate is the rate that exactly discounts estimated future cash payments (including all fees and points paid or received that form an integral part of the effective interest rate, transaction costs and other premiums or discounts) through the expected life of the financial liability, or (where appropriate) a shorter period, to the net carrying amount on initial recognition.

Derecognition of financial liabilities

The Project derecognises financial liabilities when, and only when, the Project’s obligations are discharged, cancelled or they expire. The difference between the carrying amount of the financial liability derecognised and the consideration paid and payable is recognised in profit or loss.

# COMESA - Great Lakes Trade Facilitation Project

Notes to the financial statements (continued)

for the year ended 31 December 2017

In United States Dollars.

17	Significant accounting policies (continued)

(f)	Foreign currency

In preparing the financial statements, transactions in currencies other than United States Dollar are recorded at the middle rates of exchange at the date the transaction first qualifies for recognition.

At each reporting date, monetary items denominated in foreign currencies are retranslated at the rates prevailing at the reporting date. Non-monetary items carried at fair value that are denominated in foreign currencies are retranslated at the rates prevailing at the date when the fair value was determined. Non-monetary items that are measured in terms of historical cost in a foreign currency are not retranslated.

Foreign exchange differences are recognised in income and expenditure statement in the period in which they arise.

APPENDIX I –

COMESA - Great Lakes Trade Facilitation Project

Comparison of actual to budgeted expenditure

| MAIN ACTIVITIES | SUB-ACTIVITIES | BUDGET | ACTUAL | VARIANCE | COMMENTS |
| --- | --- | --- | --- | --- | --- |
|  |  | US$ | US$ | US$ |  |
| COMPONENT 2: Implementation of policy & procedural reforms and capacity building to facilitate cross-border trade |  |
| 2.1 Prepare training manuals on border management procedures, STR, rules and regulations, basic customer management, conflict resolution, gender awareness raising for cross border officials, traders associations and TIDOs. | Hire of consultant for development of Training of Trainers Manual and delivery of training. | 200,000 | - | 200,000.00 | Procurement and expenditure commitment was not finalised in accordance with work plan and budget. The Secretariat has now in 2018 recruited the consultants who have subsequently developed and delivered the manuals as well as the training. Management considers that they loss time will be fully recovered in the remaining period (2018 to 2020). |
|  | Conduct of Training of Trainers Course in project Member States namely DR Congo, Rwanda and Uganda. | 100,000 | - | 100,000.00 | The activity will be implemented after validation of Training of Trainers Manual in 2018. |
| 2.2 Preparation of a programme of training for officials at the border and traders including border management procedures, rules and regulations, basic customer management, conflict resolution, gender awareness raising for cross border officials, traders associations and TIDOs, the key principles and mechanism of the COMESA Regulations and STR. | Payment of STR consultancy fees and implementation of STR activities. | 50,000 | 30,701.00 | 19,299.00 | STR Consultant was recruited in October 2017 for six months ending in March 2018 at a monthly consultancy fee of US$ 5,067 + activities relating to STR implemented. |
|  | Convene Regional Dialogue on STR | 107,352 | 86,538.15 | 20,813.85 | One workshop for Regional Dialogue on STR was conducted in September 2017 in Musaze City, Rwanda. |

APPENDIX I

COMESA - Great Lakes Trade Facilitation Project

Comparison of actual to budgeted expenditure (continued)

| MAIN ACTIVITIES | SUB-ACTIVITIES | BUDGET | ACTUAL | VARIANCE | COMMENTS |
| --- | --- | --- | --- | --- | --- |
|  |  | US$ | US$ | US$ |  |
| COMPONENT 2: Implementation of policy & procedural reforms and capacity building to facilitate cross-border trade |  |
| 2.3 Support the dissemination and application of the COMESA Regulations on Minimum Standards for the treatment of Small Scale Cross Border Traders & COMESA Simplified Trade Regime (STR) through the Trade Information Desks (TIDs). | Conduct of training for Trade Information Desk Officers(TIDOs) | 100,000 | 77,418.74 | 22,581.26 | Two training of TIDOs had been conducted in 2017 namely one in June 2017 in Rubavu, Rwanda and the second in Lusaka, Zambia in November 2017. |
| 2.4 Coordination of GLTFP at selected border posts in DR Congo, Rwanda and Uganda. | Payment of emoluments for TIDOs at selected border posts in DR Congo (10), Rwanda (4) and Uganda (6). | 87,000 | 59,000.00 | 28,000.00 | Fourteen TIDOs were recruited in May 2017 and another four TIDOs were recruited in October 2017. The project has still not yet recruit TIDOs for Goli border posts which will be done in January 2018. |
| 2.5 Establishment of GLTFP at selected border posts in DR Congo, Rwanda and Uganda. | Purchase of office furniture and office equipment for TIDOs | 88,092 | 65,093.06 | 22,998.94 | Office furniture, PCs, printers and smart phones were delivered to 18 TIDOs in November 2017. |
|  | Payment of running costs of TIDOs at border posts. | 18,000 | 5,361.71 | 12,638.29 | Expenditure relates to the purchase of printers and stationery for TIDOs. |
|  | Purchase of solar panel for TIDO offices | 15,000 | - | 15,000.00 | Implementation of the activity is in progress. Quotations for solar panels have been received and will be finalised in 2018. |
|  | Recruitment of TIDOs | 20,000 | 9,530.70 | 10,469.30 | Mission for recruitment of TIDOs undertaken in May 2017. |

APPENDIX I

COMESA - Great Lakes Trade Facilitation Project

Comparison of actual to budgeted expenditure (continued)

| MAIN ACTIVITIES | SUB-ACTIVITIES | BUDGET | ACTUAL | VARIANCE | COMMENTS |
| --- | --- | --- | --- | --- | --- |
|  |  | US$ | US$ | US$ |  |
| COMPONENT 2: Implementation of policy & procedural reforms and capacity building to facilitate cross-border trade |  |
| 4.1 Implementation of the Project Communication Strategy. | Hire of consultant for the development of project communication and advocacy strategy. | 30,000 | - | 30,000.00 | The contract of consultants for the development of GLTFP Communication & Advocacy Strategy was finalised in December 2017. First payment of 20% of fees was made after presentation of Inception Report in January 2018. |
|  | Implementation of project communication and advocacy strategy. | 129,000 | 33,978.92 | 95,021.08 | Amount being purchase of uniform for TIDOs, printing of brochures, banners, conference bags for visibility of the project. |
|  | Hire of consultant for development of GLTFP website | 24,500 | 12,250.00 | 12,250.00 | Implementation of the activity is in progress. GLTFP website will be online in 2018. |
|  | Maintenance of GLTFP website | 5,000 | - | 5,000.00 | Implementation of the activity depends on the finalisation of GLTFP website. |
| 4.2 Creation of a portal on COMSAT and populating the portal with statistics gathered using the standardised regional practices for collecting and reporting on Small Scale Cross Border Trade ( SSCBT). | Hire of consultant to develop the GLTFP web-based portal as part of COMSAT | 50,000 | - | 50,000.00 | Activity is in progress. |
| 4.3 Development of standardised regional practices for collecting and reporting data on Small Scale Cross Border Trade ( SSCBT). | Purchase of Android Tablets to be used to collect data from a pilot target border area. | 17,000 | - | 17,000.00 | The project will no longer purchase Android Tablets for enumerators. Instead Member States will buy for their own numerators. |
|  | Hire consultant to develop Mobile Application | 10,000 | - | 10,000.00 | The mobile application had been developed in house by IT Department. Thus no expenditure incurred under this activity. |

APPENDIX I

COMESA - Great Lakes Trade Facilitation Project

Comparison of actual to budgeted expenditure (continued)

| MAIN ACTIVITIES | SUB-ACTIVITIES | BUDGET | ACTUAL | VARIANCE | COMMENTS |
| --- | --- | --- | --- | --- | --- |
|  |  | US$ | US$ | US$ |  |
| COMPONENT 2: Implementation of policy & procedural reforms and capacity building to facilitate cross-border trade |  |
| 4.4 Enhance capacity of Member States on the use of standardised regional practices for collection and reporting on SSCBT data. | Convene regional workshop on harmonisation of ICBT Data | 100,000 | 66,004.87 | 33,995.13 | Workshop on harmonisation of informal cross border trade statistics data was conducted in July 2017 in Kigali, Rwanda. |
| 4.5 Support implementation of project monitoring and evaluation (M&E) activities. | Support implementation of project M&E activities. | 11,000 | - | 11,000.00 | Part time M& E Expert has not yet been recruited. This activity will be implemented in 2018. |
|  | Participation of M& E Expert in cross border surveys. | 10,000 | 9,750.00 | 250.00 | This activity will be implemented after the recruitment of part time M & E expert. The expenditure relates to the assessment mission which was conducted in March 2017. |
| 4.7 Coordination of GLTFP at COMESA Secretariat | Payment of staff emoluments for Project Coordinator, Project Accountant, Procurement Expert and Regional TIDOs. | 243,700 | 222,698.99 | 21,001.01 | All the four staff of the project implementation team were recruited in 2017 with the Procurement Expert joining in January 2017 and the Project Accountant and Regional TIDO joining in April and October 2017 respectively. |
|  | Supervision mission by Regional TIDO as project border posts. | 20,000 | 19,033.53 | 966.47 | Supervision mission was undertaken in November 2017. |
|  | Capacity building of project staff to enhance their capacity in delivery of their mandate. | 50,000 | 9,711.47 | 40,288.53 | During the year the Project Accountant attended a financial management training course in Kenya in April 2017.The Procurement Expert and Project Coordinator attended training in Lusaka organized by World Bank Office of Zambia. |

APPENDIX I

COMESA - Great Lakes Trade Facilitation Project

Comparison of actual to budgeted expenditure (continued)

| MAIN ACTIVITIES | SUB-ACTIVITIES | BUDGET | ACTUAL | VARIANCE | COMMENTS |
| --- | --- | --- | --- | --- | --- |
|  |  | US$ | US$ | US$ |  |
| 4.8 Establishment of GLTFP offices at COMESA Secretariat | Payment of running costs for project staff | 15,000 | 12,247.31 | 2,752.69 | Amount being purchase of printings and stationery for PIU staff at COMESA Secretariat & other operating costs such as bank charges and translation fee of documents. |
|  | Purchase of office equipment | 15,000 | 5,921.62 | 9,078.38 | Amount pertains to office furniture and office equipment purchased in March 2017. |
|  | Recruitment and installation costs | 20,000 | 12,307.20 | 7,692.80 | Installation costs for Project Coordinator and Project Accountant was paid in November 2017. |
| 4.9 Compile and issue of annual mandatory accounts and financial statements for 2016 | Facilitate the conduct of statutory external audit for 2016. | 7,500 | 1,000.00 | 6,500.00 | Audit of GLTFP for the year 2016 was conducted by KPMG at a total cost of US$ 1,000. |
| 4.10 Facilitate implementation of project and review of policy documents. | Convene Project Steering Committee Meeting | 50,000 | 50,979.90 | (979.90) | Two RCC Meetings were conducted during the year namely the first one in Kampala, Uganda in June 2017 and second one in Kigali, Rwanda in December 2017. |
| 4.11 Facilitate policy coordination and coordinate project implementation. | Convene Project Steering Committee Meeting | 600 | 632.90 | (32.90) | Four PSC meetings were conducted at the COMESA Secretariat in 2017. |
| TOTAL ( US $) - COMPONENT 2 & COMPONENT 4 |  | 1,593,744 | 790,160.07 | 803,583.93 |  |
| NOTES TO TABLE: |  |  |  |  |  |
| 1. The total expenditure for 2017 amounts to US$ 790,160.07which represents a consumption rate of 49.6% of the total budget for 2017. |

APPENDIX II

# COMESA - Great Lakes Trade Facilitation Project

Schedule of fixed assets

for the year ended 31 December 2017

| 2016 |  |  |  |
| --- | --- | --- | --- |
| Asset Code | Item | Year | Amount |
| CWB/OEI003 | LAPTOP | 2016 | 1 890 |
| CWB/OEI004 | LAPTOP | 2016 | 1 890 |
| CWB/OEI005 | LAPTOP | 2016 | 1 890 |
| CWB/OEI006 | PRINTER | 2016 | 407 |
| CWB/OEI007 | DESKTOP COMPUTER | 2016 | 1 309 |
| CWB/OEI008 | DESKTOP COMPUTER | 2016 | 1 309 |
| CWB/OEI009 | DESKTOP COMPUTER | 2016 | 1 309 |
| Total computer equipment |  |  | 10 004 |
| CWB/OEI007 | HEAVY DUTY PRINTER | 2016 | 2 199 |
| CWB/OES004 | SCANNER | 2016 | 382 |
| Total office equipment |  | 2016 | 2 581 |
| 2017 |  |  |  |
| Asset Code | Item | Year | Amount |
| CWB/OFD001 | EXECUTIVE DESK | 2017 | 722 |
| CWB/OFD002 | EXECUTIVE DESK | 2017 | 722 |
| CWB/OFC001 | H.B CHAIR | 2017 | 445 |
| CWB/OFC002 | H.B CHAIR | 2017 | 445 |
| CWB/OFC003 | VISITORS CHAIR | 2017 | 329 |
| CWB/OFC004 | VISITORS CHAIR | 2017 | 329 |
| CWB/OFC005 | VISITORS CHAIR | 2017 | 329 |
| CWB/OFC006 | VISITORS CHAIR | 2017 | 329 |
| CWB/OFC007 | EXECUTIVE CHAIR | 2017 | 877 |
| CWB/OFA001 | OPEN SHELF | 2017 | 266 |
| CWB/OFA002 | OPEN SHELF | 2017 | 266 |
| CWB/OFA003 | OPEN SHELF | 2017 | 266 |
| CWB/OES001 | METAL STATIONERY | 2017 | 198 |
| CWB/OES002 | METAL STATIONERY | 2017 | 198 |
| CWB/OES003 | METAL STATIONERY | 2017 | 198 |
| CWB/OFD001 | OFFICE DESK | 2017 | 392 |
| CWB/OFD002 | OFFICE DESK | 2017 | 392 |
| CWB/OFD003 | OFFICE DESK | 2017 | 392 |
| CWB/OFD004 | OFFICE DESK | 2017 | 392 |
| CWB/OFD005 | OFFICE DESK | 2017 | 392 |
| CWB/OFD006 | OFFICE DESK | 2017 | 392 |
| CWB/OFD007 | OFFICE DESK | 2017 | 392 |
| CWB/OFD008 | OFFICE DESK | 2017 | 392 |
| CWB/OFD009 | OFFICE DESK | 2017 | 392 |

APPENDIX II

# COMESA - Great Lakes Trade Facilitation Project

Schedule of fixed assets (continued)

for the year ended 31 December 2017

| 2017 |  |  |  |
| --- | --- | --- | --- |
| Asset Code | Item | Year | Amount |
| CWB/OFD010 | OFFICE DESK | 2017 | 392 |
| CWB/OFD011 | OFFICE DESK | 2017 | 392 |
| CWB/OFD012 | OFFICE DESK | 2017 | 392 |
| CWB/OFD013 | OFFICE DESK | 2017 | 392 |
| CWB/OFD014 | OFFICE DESK | 2017 | 392 |
| CWB/OFD015 | OFFICE DESK | 2017 | 392 |
| CWB/OFC008 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC009 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC010 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC011 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC012 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC013 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC014 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC015 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC016 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC017 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC018 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC019 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC020 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC021 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC022 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC023 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC024 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC025 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC026 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC027 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC028 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC029 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC030 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC031 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC032 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC033 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC034 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC035 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC036 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC037 | VISITOR'S CHAIR | 2017 | 133 |
| CWB/OFC038 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC039 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC040 | OFFICE SWIVEL CHAIR | 2017 | 203 |

APPENDIX II

# COMESA - Great Lakes Trade Facilitation Project

Schedule of fixed assets (continued)

for the year ended 31 December 2017

| 2017 |  |  |  |
| --- | --- | --- | --- |
| Asset Code | Item | Year | Amount |
| CWB/OFC041 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC042 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC043 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC044 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC045 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC046 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC047 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC048 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC049 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC050 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC051 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFC052 | OFFICE SWIVEL CHAIR | 2017 | 203 |
| CWB/OFA001 | FILLING CABINET | 2017 | 273 |
| CWB/OFA002 | FILLING CABINET | 2017 | 273 |
| CWB/OFA003 | FILLING CABINET | 2017 | 273 |
| CWB/OFA004 | FILLING CABINET | 2017 | 273 |
| CWB/OFA005 | FILLING CABINET | 2017 | 273 |
| CWB/OFA006 | FILLING CABINET | 2017 | 273 |
| CWB/OFA007 | FILLING CABINET | 2017 | 273 |
| CWB/OFA008 | FILLING CABINET | 2017 | 273 |
| CWB/OFA009 | FILLING CABINET | 2017 | 273 |
| CWB/OFA010 | FILLING CABINET | 2017 | 273 |
| CWB/OFA011 | FILLING CABINET | 2017 | 273 |
| CWB/OFA012 | FILLING CABINET | 2017 | 273 |
| CWB/OFA013 | FILLING CABINET | 2017 | 273 |
| CWB/OFA014 | FILLING CABINET | 2017 | 273 |
| CWB/OFA015 | FILLING CABINET | 2017 | 273 |
| VSAQUAT1707002505 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000762 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707002178 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707002441 | SMART PHONE | 2017 | 60 |
| VSAQUAT | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000257 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707002502 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000520 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000209 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000479 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000351 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000201 | SMART PHONE | 2017 | 60 |

APPENDIX II

# COMESA - Great Lakes Trade Facilitation Project

Schedule of fixed assets (continued)

for the year ended 31 December 2017

| 2017 |  |  |  |
| --- | --- | --- | --- |
| Asset Code | Item | Year | Amount |
| VSAQUAT1707000783 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000244 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707002153 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000170 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000260 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707001387 | SMART PHONE | 2017 | 60 |
| VSAQUAT1707000774 | SMART PHONE | 2017 | 60 |
|  | SMART PHONE | 2017 | 60 |
|  | SMART PHONE | 2017 | 60 |
| Total office equipment |  |  | 24 189 |
| CWB/OEI031 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI032 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI033 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI034 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI035 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI036 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI037 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI038 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI039 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI040 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI041 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI042 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI043 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEI044 | DESKTOP COMPUTER | 2017 | 991 |
| CWB/OEP001 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP002 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP003 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP004 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP005 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP006 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP007 | PHOTOCOPIER/PRINTER/SCANNER | 2017 | 3 990 |
| CWB/OEP008 | PRINTER-SCANNER | 2017 | 637 |
| CWB/OEI045 | LAPTOP | 2017 | 807 |
|  | UPS | 2017 | 3 578 |
| Total computer equipment |  |  | 46 826 |