COUR DE JUSTICE

COMESA

# مـــــحـكمـة العــــــدل

- COURT OF JUSTICE

Distr.

RESTRICTED

CS/ADM/SC/XXII/7.2

October 2019

Original:  ENGLISH

COMMON MARKET FOR EASTERN AND

SOUTHERN AFRICA

Twenty Second Meeting of the Sub Committee on

Audit and Budgetary Matters

Lusaka, Zambia

28 October – 1 November 2019

DRAFT

COMESA COURT OF JUSTICE WORK PROGRAMME AND DRAFT BUDGET FOR 2020

Theme: “Ensuring Economic Integration by Bringing Justice to the Common Market”

- (NLM/sk)

- INTRODUCTION

- The Court of Justice of the Common Market for Eastern and Southern Africa (COMESA Court of Justice) was established in 1994 under Article 7 of the COMESA Treaty as one of the Organs of COMESA. The Court is comprised of two Divisions; the Appellate Division and the First Instance Division. The Court is composed of twelve Judges five of whom constitute the Appellate Division and seven constitute the First Instance Division. The day-to-day operations of the Court are co-ordinated through a Court Registry which is headed by a Registrar.

- The Court sits on an ad hoc basis but holds Administrative Meetings to discuss strategic issues and make decisions on policy issues concerning the Court. Pursuant to Rule 4(1) of the Rules of Court (2016), the Court may hold its court sessions in any Member State on need basis.

- Mandate of the Court

- The Court’s primary function is to uphold the rule of law in the enforcement of the COMESA Treaty by ensuring adherence to the law in the interpretation and application of the Treaty. Its general jurisdiction is to adjudicate, give advisory opinions and arbitrate on any matters that may be referred to it under the Treaty. These matters may be between Member States, Member States and the Council, the Common Market and Member States, between legal and natural persons resident in Member States or between COMESA or its institutions and their employees.

- OBJECTIVES OF THE 2020 WORK PROGRAMME

- Based on the 2016-2020 Medium Term Strategic Plan of the Court, the 2020 Work Programme will be achieved through addressing the following strategic issues, priority areas and objectives over the implementation period:

- Dispensation of Justice

- Dispensation of justice is the determination of matters brought before the Court in accordance with the Treaty and principles of International Law to ensure adherence to the rule of law within the COMESA region. In the discharge of this mandate, the Court must take cognisance of the diversity of cultures, legal traditions and languages within the region.

- To improve dispensation of justice, the Court will pursue the following objectives:

    - Improve access to justice by eliminating unnecessary barriers that impede easy access to its services;

    - Ensure timely disposition of cases;

    - Enhance the quality of justice through accurate interpretation of applicable laws and facts; and

    - Enhance the trust and confidence in the Court by strengthening its impartiality and independence.

- Communication and Public Awareness

- The Court recognises that public awareness of its services is a critical component of access to justice. This entails the dissemination of information and raising awareness and level of knowledge of the public which is a prerequisite in mobilising their participation in the judicial process of COMESA. In 2019, the Court continued its public awareness activities and intends to increase stakeholder awareness in 2020.

- To enhance communication and public awareness, the Court will pursue the following objectives:

- Raise stakeholder awareness and their knowledge of the Court;

- Develop, promote and maintain coherent and consistent corporate brand and identity;

- Inculcate a sense of regional ownership of the Court by Member States thereby promoting a sense of national and regional pride.

- Institutional Strengthening

- Inadequate capacity of the Court is a fundamental challenge that must be addressed for the organisation to deliver on its mandate. Specific concerns surrounding this strategic issue include:

- Inadequate organisational structure of the Court;

- Inadequate human and financial resources; and

- Inadequate human resource development.

- Under this Strategic Issue, the Court will pursue the following objectives:

- Develop and implement a sustainable organisational structure;

- Improve knowledge and skills;

- Improve the Court registry;

- Enhance resource mobilisation by building a sustainable resource base to support implementation of the Strategic Plan;

- Improve governance of the court through the development and adoption of principles of good governance; and

- Implement a monitoring and evaluation (M&E) system for regular assessment and feedback in the implementation of the Strategic Plan.

- ICT Optimization

- The Court recognises the immense potential of ICT as a key enabler in the improvement of the administration of justice. Optimal utilisation of ICT can enable quicker dispensation of justice and enhance the efficiency and effectiveness of administrative processes such as storage and retrieval of information.

- An automated case-flow management system guarantees easy access to information and safe custody of records thereby enhancing public trust in the judicial process. In January 2019, the Court, with support from Microsoft, deployed and implemented an Electronic Evidence Management System (EMS) called CaseLines. In 2020, the Court will endeavour to achieve ICT optimisation by developing and implementing innovative Information and Communication Technology (ICT) systems.

- MAIN ACTIVITIES UNDERTAKEN BY THE COURT INCLUDING CHALLENGES FACED AND REMEDIAL MEASURES PUT IN PLACE IN 2019

Activities

- In 2019, the Court continued implementing both its Medium-Term Strategic Plan, 2016–2020 (MTSP 2016-2020) and its 2019 Work Programme. The Court held eight court sessions in respect of the following cases:

- Miscellaneous Application No 1 of 2018;

- Appeal No 1 of 2018;

- Taxation Cause No 1 of 2018;

- Appeal No 1 of 2019 arising from Reference No 1 of 2017;

- Miscellaneous Application No 2 of 2018; and

- Restoration Application No 1 of 2018.

- The Court participated to different publicity seminars and workshops inter alia:

- A retreat for Honourable Judges;

- Tralac Annual Conference;

- Training for Senior Registry Staff on Enterprise Risk Management;

- The Commonwealth Lawyers Conference;

- The African Arbitration Association Conference;

- International Conference on Role of Case Management System for Justice: System Integration, Performance and Country Development;

- Source21 COMESA Trade Fair and High-Level Business Summit;

- The Law Society of Kenya Annual Conference;

- Training Session on Judicial Case Management & Ethics for some Honourable Judges and senior Registry Staff which was done in collaboration with the Commonwealth Magistrates and Judges Association and the Civil Service College, UK; and

- Two Judges attended the Commonwealth Magistrates and Judges Association Annual Conference in Papua Guinea.

- The Court has finalised interviews for the positions of Clerk of Court and Internal Auditor. The positions of two Administrative Assistants were filled in February and April this year although one of them is on temporary basis. The position of Receptionist and Switch Board Operator became vacant in April this year and is yet to be filled.

- As mentioned above, in January 2019, the Court, with support from Microsoft, deployed and implemented an Electronic Evidence Management System (EMS) called CaseLines. This was a major achievement since filing of documents could now be done without the need for parties to travel to the Court for physical filing. Equally important, Judges are now able to access the bundle of evidence any time and from anywhere.

- From July 2019, the Court started using its own domain name www.comesacourt.org   for email addresses for Honourable Judges and Court Staff. This will enhance the security and privacy of communication between the Honourable Judges and the Registry and vice versa and amongst Judges. The website of the Court has also been revamped, enhanced and is now up to date.

Challenges faced during the implementation of planned activities and remedial measures put in place to mitigate some of the challenges faced in 2019

- The Court continues to face some difficulties in operating at its permanent seat.  Some of the challenges arise from the economic embargo imposed on the Host Member State. Due to this challenge, the Court has continued maintaining and operating most of its financial affairs from Lusaka, Zambia. Further, owing to these difficulties, the Court has had to carry out most of its activities such as court sessions and other meetings away from the Seat. There is also the issue of non-availability of genuine software and hardware applications due to the economic embargo. As a result, the Court has been restricted to acquiring and using software and hardware that are not affected by the economic embargo

- The Host Member State has experienced political challenges from around the end of 2018 to around the end of the first half of 2019. These challenges posed some operational as well as administrative difficulties for the Court. The smooth operations of the Court were, as a result, adversely affected. This included implementation of some of the planned activities for 2019. In the wake of the political challenges that were experienced by the Host Member State, the Court took administrative measures to ensure continuation of some activities particularly court sessions.

- Delay or non-remittance of budgetary contributions by some Member States has been particularly acute in 2019. During the period 01 January–28 August 2019, the Court had received a total amount of COM$1,904,938. Out of this amount, only COM$457,337 was received towards the 2019 budget representing a 16.39% of the 2019 Budget of COM$2,789,793.  The remaining balance of the total amount received in 2019 amounting to COM$1,447,600 was received towards arrears representing a receipt of 30.26% of arrears outstanding as at 1st January 2019 of COM$4,784,584. There are also still not enough Cooperating Partners coming forward to support the Court in its programmes.

- The Court continued exploring other means of mobilising contributions from Member States and with efforts to identify more Cooperating Partners who could support the Court.

- Lack of adequate staff to support the implementation of the planned work programme has also been a challenge. However, with the upcoming Human Resources review exercise, this problem will be resolved. The Court is carrying out a review of human resources organisational structure needs of the Court and has continued with the use of temporary assistance including seeking assistance from the Secretariat in implementing some of the Court’s work programmes.

- Delay by the Host Government to resolve the issue of the title deeds for the Court building and other handover documents for the other assets handed over to the Court has continued to hamper the operations of the Court. The roof of the court building has been leaking since the building was handed over in 2014. Promises have been made to carry out repairs, but this has not happened. Unfortunately, the Court is not able to carry out any major repairs due to the outstanding issue of ownership.

- FOCUS FOR 2020

- In 2020, the Court will continue implementing both its Medium-Term Strategic Plan, 2016–2020 (MTSP 2016-2020) and its 2020 Work Programme, and will focus on the following areas:

- The Court will continue seeking the required resources to enable it to carry out publicity seminars in Member States, hold regular court sessions and meetings. Efforts will also be made to get some cooperating partners to support ICT optimisation particularly towards making court processes largely paperless;

- Working with the COMESA Secretariat, the Court will continue with efforts to mobilise contributions from Member States and extra budgetary resources to finance the Court’s activities;

- Identify areas where skills building for Honourable Judges and members of staff of the Registry is required and partner with competent persons and/or firms to implement required training programs;

- Continue improving the Court’s governance structure and institutional development to ensure that the Court plays its role effectively and efficiently;

- Review the current Medium-Term Strategic Plan, 2016–2020 (MTSP 2016-2020); and

- Fast track the Court’s ICT optimisation program in order to facilitate and enhance research, communication, publicity, accessibility of its services and service delivery. The Court will continue to promote the use of CaseLines Evidence Management System among Judges and court users.

- The Meeting is invited to take note of the key outputs and activities that will be realised within the year as part of the implementation of the MTSP 2016-2020 as highlighted and shown in Table III.

Recommendation

- It is recommended that the proposed 2020 Work Programme of the COMESA Court of Justice be considered by the Administrative Meeting.

- THE COMESA COURT OF JUSTICE 2020 DRAFT BUDGET

- The Court of Justice 2020 draft Budget will cover the period January to December 2020 and is based on the Court’s five-year 2016 – 2020 Medium Term Strategic Plan (MTSP) and the 2020 Work Programme (WP).

CHALLENGES FACED BY THE COURT AT ITS PERMANENT SEAT IN KHARTOUM, SUDAN

- The challenges faced by the Court have been highlighted under paragraph 18-23 above.

- 2020 BUDGET PROPOSAL

- The COMESA Court of Justice proposes a budget of COM$2,838,321 for 2020. This budget has taken into consideration key factors which include the following:

- COMESA Treaty Provisions and Financial Regulations

- The budget has been prepared in accordance with Article 42 of the COMESA Treaty, as read with Chapter II of the COMESA Court of Justice Financial Regulations.

- Approved ceiling by Council

- The decision by Council that the overall increase on proposed recurrent budgets from current approved budgets should not be more than 5%.

- Court Sessions, Regular Meetings and Staff emoluments

- The proposed budget has considered the core business of the Court, namely court sessions for both Divisions of the Court and regular Administrative Meetings. Honourable Judges’ allowances have been calculated based on their current conditions of service as approved by Council.  Staff emoluments have been calculated based on the Staff Rules and Regulations and staff contracts.

- Pursuant to Rule 4(1) of the Rules of Court (2016), the Court may hold its court sessions in any Member State on need basis, and in 2020, the Court expects to hold a minimum of four court sessions for each Division. The sessions would, as far as possible, be held together with Administrative Meetings, Publicity Seminars and Trainings to maximise on budget line synergies.

- Implementation of the 2016 – 2020 Medium Term Strategic Plan (MTSP)

- The Meeting is invited to note that the 2020 budget will be the fifth of the five-year annual budgets that should be prepared to finance the envisaged annual work programmes that will be derived from the 2016 – 2020 Medium Term Strategic Plan (MTSP). The 2020 Work Programme (WP) and budget of the Court will ensure that the Court’s attention is focused on key areas within the Court’s 2016–2020 MTSP.

COMESA Court of Justice Budgeting process

- The budgeting process for the COMESA Court of Justice:

- is done in accordance with the COMESA Treaty provisions and the Financial Regulations of the Court. It considers the focus areas of the Court’s Medium-Term Strategic Plan (MTSP) and the Work Programmes and uses to the extent possible: Activity Based Costing (ABC) and Activity Based Budgeting (ABB) methods. The Budget covers the period from 01 January to 31 December of 2020;

- is a fully participatory process which is in line with the provisions of the Financial Regulations and enhances and improves the quality of budget preparations; facilitates decision making processes; and ensures that the efforts of the Court are directed towards achieving its planned work programme for the year being budgeted for. It involves extensive discussions and consultations; and

- includes critical factors of the Court’s budgeting process namely accountability and timely communication through reporting. The Council, through the Judge President, is kept informed of actual results, as compared with targets.

The 2020 Expenditure Budget

- The 2020 budget has considered the ability of Member States to honour their financial obligations. Activity Based Costing and Activity Based Budgeting have been used to the extent possible in preparing the 2020 budget. Tables IV to VIII below and the accompanying Note I as well as Notes II to IV provide more details on the 2020 budget.

- The Notes and Tables give more details as they explain any increases or downward revisions on each individual budget line. They further explain why other budget lines have been maintained at the 2019 budget levels.

- The level of expenditure as at 31 August 2019, has been used to forecast some of the expenditures which are supportive or recurrent in nature. During the remaining period of September to December of the 2019 budget, the Court will continue implementing its 2019 Work Programme in line with its approved budget. The estimated expenditure during this period has also been considered in preparing the 2020 draft budget.

Income Budget

### Pre-Conditions for Realising the 2020 Budget Objectives

- For the COMESA Court of Justice to achieve the targets for the 2020 Work Programme and Budget, the following conditions which are interdependent need to be observed:

- Assessed contributions should be received as per the provision of the COMESA Treaty, i.e., 50% in January and the balance by the end of June of a financial year. This will ensure that the Court has sufficient and timely contribution resources;

- Continued strengthening of the COMESA Court so that it has the capacity to deliver its mandate;

- Efficient and effective delivery of services by the COMESA Court of Justice; and

- The Court should ensure that an efficient monitoring and evaluation mechanism is implemented.

### II.	Member States Assessed Contribution for 2020

- The source of income for the COMESA Court of Justice budget is Member States’ contributions as provided for in Article 42 (1) of the COMESA Treaty. The formula of contributions to the COMESA Court budget is in accordance with Article 42 (2) of the COMESA Treaty which states that; “The formula for contributions to the budget for the Court shall be the formula applicable to the determination of contributions by Member States to the budget of the Secretariat.” The applicable formula for contribution to the 2020 COMESA Court of Justice budget therefore is as approved by the Twentieth Meeting of the Council of Ministers as provide in Table I below:

Table I

Applicable Formula for Member States Assessed Contribution for 2020

| Gross Domestic Product (GDP) | 30% |
| --- | --- |
| Imports from non-COMESA Countries | 30% |
| Intra COMESA Exports | 30% |
| GNP per Capita | 05% |
| Population | 05% |

- The Meeting is invited to note that based on the above approved formula, Council approved the Upper Ceiling of 12% and the Lower Ceiling (floor) of 1%.

- The Meeting is further invited to note that the unit of currency of the COMESA Court of Justice budget is the COMESA Dollar as approved by Council in accordance with Article 42 (4) of the COMESA Treaty. Based on the above and the recommended assessment ratios by Council, the proposed budget shares for 2020 are as shown in Table II below. The Table also shows a comparison of the 2019 and 2020 Member States’ contribution ratios and assessed contributions.

Recommendations

- It is recommended that:

- the proposed 2020 Budget of the COMESA Court of Justice amounting to COM$2,838,321 be considered by the Sub – Committee on Audit and Budgetary Meeting for submission to the Policy Organs for approval; and

- Member States be urged to pay their assessed contributions for 2020 to the COMESA Court of Justice in accordance with Articles 42 and 166 (6) of COMESA Treaty.

Table III

COMESA COURT OF JUSTICE 2020 WORK PROGRAMME AND COST ESTIMATES (BUDGET)

TIME FRAME – 01 January to 31 December 2020

| Initiatives | Responsibility | Expected Outcome | Justification | Source of Funding | Indicative Cost |
| --- | --- | --- | --- | --- | --- |
| STRATEGIC ISSUE 1: DISPENSATION OF JUSTICE |  |  |  |  |  |
| OBJECTIVE: IMPROVE ACCESS TO JUSTICE |  |  |  |  |  |
| ICT optimisation through use of CaseLines, an Evidence Management tool, as well as the implementation of a case flow management system | Registrar | Increase in: - Members of public having access to information about the Court - Number of references and arbitral cases filed increased - Judges able to access files online through a dedicated portal - No more need to carry physical files when the Court is sitting away from its Seat - Reduction in cost of litigants, counsel or agents travelling to Khartoum to file cases | - Reduction in cost of litigating in the CCJ - Judges will have real-time access to all pleadings or documents filed in pending cases - Risk of losing physical files minimised | Court of Justice | $15,000 |
| OBJECTIVE: TIMELY DISPOSITION OF CASES |  |  |  |  |  |
| Develop, implement and monitor a case flow management and other relevant Management Information Systems Hold court sessions as, when and where required | Judges and Registrar | - Reduction of time it takes to handle and finalise cases - Reduction in number of adjournments - Improved clearance rate at all levels - Increased number of court sessions | - A case flow management system will result in expeditious resolution of disputes, reduce litigation costs and empower all stakeholders in the litigation process to contribute to the expeditious disposal of disputes. - Holding court sessions as and when required will enhance dispensation of justice and promote timely disposal of matters | Court of Justice | $550,000 |
| OBJECTIVE: ENHANCE THE QUALITY OF JUSTICE |  |  |  |  |  |
| Enhance legal research facilities for Honourable Judges and the public through the establishment of a modern resource and information centre Recruit legal researchers Undertake regular training programs | Registrar | - Enhance quality of jurisprudence emanating from the Court - Increase the use of cases decided by the Court as precedents - Increased number of referrals to the Court | - Legal research facilities and regular training programs will result in better quality judgments/ rulings/ arbitration awards. - Recruiting legal researchers will reduce time taken in finalizing cases given the ad hoc nature of the court. | Court of Justice | $25,000 |
| OBJECTIVE: ENHANCE THE TRUST AND CONFIDENCE IN THE COURT |  |  |  |  |  |
| Engage and sensitise Member States, COMESA Organs and institutions | Judges and Registrar | Increased number of cases filed in the Court Enhancement of positive perception of the Court and its usefulness - Increased percentage of judgments enforced | Sensitisation of Member States, COMESA Organs and institutions will result in increased trust and confidence in the Court which is key to the regional integration agenda | Court of Justice | $100,000 |
| STRATEGIC ISSUE 2: COMMUNICATION AND PUBLIC AWARENESS |  |  |  |  |  |
| OBJECTIVE: RAISE STAKEHOLDER AWARENESS AND KNOWLEDGE OF THE COURT |  |  |  |  |  |
| Develop a communication strategy Set-up an information resource centre Undertake publicity seminars/ workshops Optimise the use of online media communications (websites, social media) | Registrar/ Corporate/ Communications Officer of Secretariat/IT Officer | - Increased awareness, public trust and confidence in the Court - Increased number of cases filed - Increased number of enquiries about the Courts services - Increased number of mentions in the media (media monitoring) | - Undertaking publicity seminars will enhance public experience with the Court as they will become aware of role of the Court and the remedies it can afford litigants. - Optimising use of online media communication and websites will increase public awareness of the Court, its activities and services - It will assist in widely disseminating rulings and judgments of the Court | Court of Justice | $95,000 |
| OBJECTIVE: PROMOTE AND MAINTAIN COHERENT AND CONSISTENT CORPORATE BRAND AND IDENTITY |  |  |  |  |  |
| Develop and implement a branding practice manual | Registrar | - Increased number of people using the brand - Increased awareness of the public about the Court as a brand | To preserve a vibrant and contemporary brand of the Court and create awareness to the public | Court of Justice | $15,000 |
| OBJECTIVE: INCULCATE A SENSE OF REGIONAL OWNERSHIP OF THE COURT BY MEMBER STATES |  |  |  |  |  |
| Engage Member States to ensure ownership Undertake publicity seminars/ workshops with a focus on strengthening ownership Establish linkages with key stakeholders and particularly the business community to reinforce ownership of the Court. | Judges and Registrar | - Increase in the number of successful contacts established - Increased number of MS submitting contributions on time - Increased number of cases filed - Increase in the number of stakeholders citing CCJ as a forum for dispute resolution | Engaging Member States and key stakeholders will increase trust and confidence in the Court which is key in regional integration | Court of Justice | $30,000 |
| STRATEGIC ISSUE 3: INSTITUTIONAL STRENGTHENING |  |  |  |  |  |
| OBJECTIVE: DEVELOP AND IMPLEMENT A SUSTAINABLE ORGANIZATIONAL STRUCTURE |  |  |  |  |  |
| Establish human capital requirements /HR needs assessment of the Court Deploy a Talent Management System (recruitment, development, retention and reward) Implement a performance management system | Registrar/ Director HR and Administration of Secretariat | - Submission and adoption of HR needs assessment report - Populate the organisation structure (Establishment) - Institutionalisation of a Talent Management System - Institutionalisation of Performance Management System | - Implementation of talent and performance management systems will enhance effective delivery of Court services - Human resource needs assessment of the Court will identify priority vacancies to be filled given that the Court is understaffed | Court of Justice | 200,000 |
| OBJECTIVE: IMPROVE KNOWLEDGE AND SKILLS |  |  |  |  |  |
| Undertake training needs analysis Develop and implement a capacity development program Establish a collaboration mechanism and relationship with similar courts | Registrar/ Director HR and Administration of Secretariat | - Submission of and adoption of a training needs assessments report (gap analysis) - Increase in the number of Judges and staff members certified - Approval and adoption of training curriculum and programs for both Judges and employees. | - To identify gaps between current and the required levels of knowledge within the Court - To assist in the formulation of a training plan to fill the gap - Collaboration with similar courts will keep the Court up to date with current international legal practices and mechanisms for dispute resolution and promote regional integration | Court of Justice | $25,000 |
| OBJECTIVE: IMPROVE GOVERNANCE OF THE COURT |  |  |  |  |  |
| Implement case flow management and other relevant Management Information Systems Improve record keeping Enhance communication between the Judges and the Registry Review staff and financial rules and regulations Undertake regular internal and external audits Develop and implement a code of conduct for judges | Judges and Registrar | - Case management and other relevant Management Information Systems implemented - New record safe keeping system adopted - Ease of access to filed resources instantly - Identification and location of lost / misplaced documents - Reduction in number of complaints - Terms and Conditions Framework adopted (including staggering of appointment of Judges) - Code of conduct for Judges developed and implemented - Staff and Financial Rules and Regulations reviewed - Corrective actions on audits undertaken - Risk Management Policy developed and implemented | - Case flow management and other relevant Management Information Systems will result in expeditious resolution of disputes, reduce litigation costs and empower all stakeholders in the litigation process to contribute to the expeditious disposal of disputes - Undertaking regular internal and external audits will strengthen internal controls within the court ensure prudent financial and risk management - Review of the financial and staff rules to reflect current working conditions and to reconcile them with the Treaty and other similar Court instruments will enhance governance - Improved record keeping will promote accountability, transparency and accessibility of legal records to Court users | Court of Justice | $30,000 |
| OBJECTIVE: ENHANCE RESOURCE MOBILISATION |  |  |  |  |  |
| Establish a collaboration mechanism with development partners Improve communication with Member States Develop a Risk Management Policy | Registrar/ Administration and Finance Officer | - Number of timely contributions by MS - percentage increase in MS funding - percentage increase in Development Partners - percentage increase in funding (External Funding) - Member States arrears reduced | To facilitate timely achievement of the Courts activities through realising timely contributions from Member States A Risk Management Policy will reduce the likelihood of risks occurring and where they do, reduce the impact thereof | Court of Justice | $15,000 |
| OBJECTIVE: IMPLEMENT AN M&E SYSTEM |  |  |  |  |  |
| Prepare an M&E plan Implement M&E system | Registrar/M&E Officer of Secretariat | Utilisation of the M&E system to derive reports periodically | To assess whether set targets of the Court have been achieved and to promote transparency within the organization | Court of Justice | $5,000 |
| STRATEGIC ISSUE 4: ICT OPTIMIZATION |  |  |  |  |  |
| OBJECTIVE: DEVELOP AND IMPLEMENT INNOVATIVE INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SYSTEMS |  |  |  |  |  |
| Develop and implement software for Court Management System Continuous enhancement of Court automation Continuous enhancement of the website | IT Officer/ Registrar | - Reliable speed of internet and internal communication - Fast data retrieval from website and another E-Systems - Increased number of calls - Reduced number of complaints | - A software for Court management will ease access and update of court files, expedite case flow, and save time by searching in a single location for documents and case files - Enhancement of Court automation will save time in finding relevant information across the whole organization | Court of Justice | $30,000 |

NOTES TO THE 2020 DRAFT BUDGET

NOTE I:	 The notes below relate to Table IV above.

- Notes Number 1 and 9 - Budget lines on Honourable Judges’ and staff emoluments; (housing, dependence, gratuity and education allowances) are based on the approved rates, contracts and the Staff Rules and Regulations);

- Notes Number 1 and 9 – Despite some increases on some staff emoluments, the overall increment on Judges’ and staff emoluments is zero;

- Note Number 2 - These budget lines have been maintained at the 2019 level to direct the Court’s resources and efforts to the 2019 focus areas which includes Court Sessions;

- Note Number 2 – Staff Welfare – This budget line is used for staff welfare related expenses including medical expenses for staff who have exhausted their annual allocations but still need further medical treatment.

- Note Number 3 - The 2020 draft budget of the Court considered the core business of the Court and the increment on this budget line is meant to ensure that this focus area is adequately funded;

- Note Number 4 – There has been an increase in participation in Technical Committees because of governance enhancement initiatives the Court has been implementing including revision of the Court’s various rules. The increase on this budget line is meant to provide requisite resources for these activities;

- Note Number 5 – The Council of Ministers at its Meeting in November 2018 at Lusaka, Zambia directed that going forward, there should be no budget provisions on miscellaneous expenses. The Court has since implemented this directive and hence no amount has been provided on this budget line;

- Note Number 6– Due to increased need for translation and transcription occasioned by an increase in court sessions, reports and publicity activities, the increase on this budget line is to finance adequately translation and transcription activities.

- Note Number 7– The Current Medium-Term Strategic Plan for the Court will be expiring at the end of 2020. The Court plans to start activities to draft the next Medium-Term Strategic Plan (MTSP) 2021-2024 and the increase on this budget line is to facilitate activities on the new Medium-Term Strategic Plan.

- Note Number 8 - The Court will continue implementing Council decisions to double up its efforts in conducting publicity seminars in Member States and the increase on this budget line is to facilitate these activities;

- Note Number 9– Fuel and Maintenance Expenditure – Following the recommendations by a Consultant who conducted a technical survey of the Court building for the determination of power requirements to guide generator installation, the Court was able to estimate a-close to actual of fuel and maintenance expenditure for the generator in 2019 and this has informed the maintenance of these budget line provisions for 2020 at the 2019 level; and

- Note number 10 - The overall increase on the recurrent budget in 2020 is 2%.

NOTE II: Table V below provides details on the draft budget for the Appellate Division of the Court.

NOTE III:  Table VI below provides details on the draft budget for the First Instance Division of the Court.

NOTE IV: Table VII below provides details on the draft budget for the Administrative Meetings of the Court. In 2020, the Court plans to have a minimum of two Administrative Meetings. The Administrative Meetings will, as far as possible, be held together with the Court Sessions, Publicity Seminars and Trainings to maximise on budget line synergies;

NOTE V: Table VIII below provides details on the draft budget for the Honourable Judges and staff emoluments.