Distribution

Limited

# COM/ALLPI/SC/XXII/3

OCTOBER 2019

ORIGINAL:  English

____________________________________________________________________________________

COMMON MARKET FOR EASTERN

AND SOUTHERN AFRICA (COMESA)

twenthy second MEETING of the Sub-Committee

on Audit and Budgetary Matters

LUSAKA, Zambia

28th OCTOBER – 1ST NOVEMBER 2019

africa Leather and Leather Products INSTITUTE

2020 PROPOSED WORK PROGRAMMES AND BUDGET

- Introduction

- Africa Leather and Leather Products was established November 1990, as an autonomous chartered Inter-Governmental Institution. ALLPI is headquartered in Addis Ababa, Ethiopia since 1993, with its own office building. It is headed by an Executive Director who reports to a Board of Directors that is appointed by Council of Ministers.

- In accordance with Articles 14 (1), (2), (6) and (7) of the Charter, the Executive Director of ALLPI is pleased to submit the 2020 ALLPI Proposed Work Programmes and Budget to the Sub-Committee on Audit and Budgetary Matters for preliminary consideration and recommendation. Article 14 (3) of the ALLPI Charter also provides that “The resources of the budget shall be derived from annual contributions of the ALLPI member States and such other sources as may be determined by the Board of Directors”.

- The 2020 fiscal year programmes of the Institute will be financed from assessed contributions of member countries and "unsecured" budget which will be secured from Development Partners as resource mobilization effort. The member States’ contribution is very important as it serves as seed capital in the fund raising drive and also covers the overall overheads and operational costs of the organization.

Key Factors Considered in the 2020 Budget of the ALLPI

4.	The following major factors have been taken into consideration in preparing the 2020 budget:

- In the year 2020, ALLPI is starting to implement the revised ALLPI Ten Years Strategic Plan (2016 - 2025) with the additional two strategic Objectives that were introduced in the revised strategy in line with the expanded continental mandate of ALLPI which require special consideration.

- The need to deliver activities that facilitate the growth and development of the Leather Value Chain in Member States;

- To facilitate and promote the strengthening of the continental leather value chain;

  - Facilitate SMEs participation in national Fairs – to attend in B2B platform in order to create market linkages for SMEs of leather sector.

- The preparation of global leather Congresses; the World Leather Congress 2021 and the International Unions of Leather Technologist and Chemists Society (IULTCS) Congress 2021 which will take place for the 1st time in the African continent

- The resource mobilization efforts have been considered to be realized during the budget year for the establishment of the Regional Design Studio which was adopted as Flagship Project during the 2016 COMESA Summit and this requires counterpart contributions from the Institute, in collaboration with its member States.

- The Year 2020 Draft Work Programme includes detailed Activities, Expected Outputs, Means and Justifications and corresponding budget, stated as secured (Regular budget) and unsecured, expected from developmental partners.  (See Table 1)

Table 1: 2020 Draft Work Programme and Budget

| SOs No. | Strategic Objective | Activities | Expected Output | Means | Time Frame Quarters |  |  |  | Justification |  | Budget |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 |  |  |  | ALLPI |  | Unsecured |  | Total |
| 1 | To enhance ALLPI capacity to share best practices and strengthen value chain networks. | 1.1 Preparing Module contents, developing delivery methods, filming, recording and editing online courses. | One module is activated for online training | Internet based applications |  |  |  |  |  | Contribute to capacity building of value chain professionals across the region in a cost-effective way | 12,000 |  | - |  | 12,000 |  |
|  |  | 1.2 Implement the summit decision of transforming ALLPI into a continental body | Summit decisions implemented | The number of summit decisions implemented |  |  |  |  |  | Enhanced compliance with the Summit decision | - |  | - |  | - |  |
|  |  | 1.3 Strengthen ALLPI to undertake Development Consultancy | - Consultancy bids at least 4 bids submitted - Data base of consultancy developed - 2 MoUs signed with international consultancy firms - Revised and enlarged list of collaborators to undertake consultancy - Incentivizing staff to do consultancy | - Visiting Research Africa websites for biding adverts - Application for bids - Method for training - Ways for incentivizing staff |  |  |  |  |  | Makes a contribution on financial resource base for ALLPI | 1,000 |  | - |  | 1,000 |  |
|  |  |  | A virtual team to aid the designing of fundraising proposals and also preparation of strategic reports established | Desk work |  |  |  |  |  | Enhance ALLPI to improve its fundraising drive in partnership with internationally recognized consultancy firms. | - |  | 10,000 |  | 10,000 |  |
|  |  | 1.4 Implement training program | Internal training: - Staff capacity built in the following areas: - Proposals writing; - Research methods, | In-house and inviting a facilitator to train experts, Out source within the host country |  |  |  |  |  | This will improve ALLPI capacity to raise resources and undertake research. | 3,000 |  | - |  | 3,000 |  |
|  |  |  | Training at least 100 SMEs in the following areas facilitated: - Clicking Technology & material Calculation of Leather Products, - Leather Footwear & Goods Design Craftsmanship & Expert Readiness - Footwear Design, Pattern Making - Total quality management activities focusing on hides and skins - Incubator design and implementation and introduction to cleaner technology - Environmental management of leather processing | - 5 national training workshops |  |  |  |  |  | Boosts skills of enterprises to manufacture quality and competitive products | 70,000 |  | 100,000 |  | 170,000 |  |
|  |  | 1.5 Facilitate the development of curricula | Curricula harmonized | Harmonization workshop and Desk Work |  |  |  |  |  | Enhances skills portability | 30,000 |  | 35,500 |  | 65,500 |  |
|  |  | 1.6 Ensure effective implementation of the Quality Management and Environmental Management Systems | Quarterly internal reviews on the adherence undertaken | Surveillance Audit and in-house implementation |  |  |  |  |  | QMS/EMS is considered as important tool for effective and efficient delivery of services by ALLPI | 3,500 |  | - |  | 3,500 |  |
|  |  | 1.7 Financial and budgetary review quarterly of ALLPI | Financial and Budgetary Matters reviewed quarterly. | Desk work |  |  |  |  |  | To ensure efficient Budget utilization | - |  | - |  | - |  |
|  |  | 1.8 Strengthen ALLPI Institutional Project management capacity and delivery service: | Internal and external Project development training program in place | consulting development partners |  |  |  |  |  | Enables Internal and external stakeholders learn Project development | - |  | 10,000 |  | 10,000 |  |
|  |  |  | Project Management and Quality Service deliver augmented. | Consultant Salary |  |  |  |  |  | Strengthen institutional capacity to manage clusters, enhance value addition and Promote market linkage to support leather development in the region | 109,320 |  | - |  | 109,320 |  |
|  |  | 1.9 Undertake M&E for the activities of ALLPI in the Region | M&E Report of at least three countries | Survey, structured and unstructured interview, focus group discussion |  |  |  |  |  | M&E is also key to an iterative management process in which implementation decisions are based on real-time monitoring information and learning from past experience (evaluative information). | 1,000 |  | - |  | 1,000 |  |
| Sub- Total (SO1) |  |  |  |  |  |  |  |  |  |  | 229,820 |  | 155,500 |  | 385,320 |  |
| 2 | To enhance value addition through Clusters/Incubators/ Service Centers development; | 2.1. Train 400 official, and SMEs representatives in Cluster Development and Management by 2025 | - 5 clusters established in Member States; - 30 persons trained in cluster designing, implementation and governance; - 30 SMEs trained in participating in government procurement tendering | Conducting regional workshops for cluster facilitator and Producing reading materials |  |  |  |  |  | Enhances the capacity of SMEs to participate in supplying big buyers for example government institutions, | 35,000 |  | 40,000 |  | 75,000 |  |
| Sub-Total (SO2) |  |  |  |  |  |  |  |  |  |  | 35,000 |  | 40,000 |  | 75,000 |  |
| 3 | To facilitate and promote the strengthening of the continental leather value chain; | 3.1. Design equipment for vegetable tanning | Designs shared with relevant stakeholders | Desk work |  |  |  |  |  | This will improve/enhance technology transfer and artisans/MSMEs accessibility to competitively priced tools, Machines and equipment | 5,000 |  | 25,000 |  | 30,000 |  |
|  |  | 3.2. Reverse engineer tanning drums for vegetable tanning | Selected Tools and equipment for vegetable tanning reverse engineered; | Desk work (Consultancy) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Selected Tools and equipment for vegetable tanning reverse engineered. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | First selected prototype tools machines and equipment launched |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.3. Facilitate SMEs participation in national Fairs | Viable trade fairs identified, updated : - B2B frame work developed - 10 SME’s facilitated to participate in in AALF 4 member states supported to organize trade fairs | Desk work mission |  |  |  |  |  | Creates business and business linkages and promotes participation in regional and international trade. | 45,000 |  | 40,000 |  | 85,000 |  |
|  |  | 3.4. Facilitate expansion of ALLPI mandate in line with Agenda 2063 and SDGs | Agenda 2063 and SDGs considerations mainstreamed in ALLPI programming | ALLPI Project Proposals involving 2063 and SDGs |  |  |  |  |  | Contribute to the attainment of the Agenda 2063 and SDGs, which has the potential to enhance fundraising. | - |  | - |  | - |  |
| Sub-Total (SO3) |  |  |  |  |  |  |  |  |  |  | 50,000 |  | 65,000 |  | 115,000 |  |
| 4 | To build and operationalize a comprehensive production and trade database for the leather sector | 4.1. Hold a regional awareness workshop on Market intelligence | Gap analysis on the capacity of MS to analyze and disseminate market intelligence undertaken | Desk work |  |  |  |  |  | The collection, analysis and dissemination of market intelligence enhanced |  |  |  |  |  |  |
|  |  |  | 15 Information market officers trained | 2 days Regional awareness workshop |  |  |  |  |  |  | 20.000 |  | 20,000 |  | 40,000 |  |
|  |  | 4.2. Sustaining Online Systems (Google Drive, Smartsheet), Subscription for the LeatherBiz.com, Devex, Crosseref, Leather Magazine, Membership fee of IULTCS, Web hosting, Software renewal, Broad Band and ITC Membership fee | Improved market intelligence and M & E System | Subscriptions |  |  |  |  |  | Improve LLPI capacity to deliver quality services, costly and effectively. | 20,000 |  | - |  | 20,000 |  |
|  |  | 4.3 Upgrade the ALLPI B2B Portal to eCommerce System in the Leather Sector | Integrated B2B portal with eCommerce system in the leather sector developed | Desk work l Communication and networking with finance and logistics service providers |  |  |  |  |  | Leather Enterprises need to have a platform to create linkages in an easy and cost-effective way | 2,000 |  | 15,000 |  | 17,000 |  |
| Sub-Total (SO4) |  |  |  |  |  |  |  |  |  |  | 42,000 |  | 35,000 |  | 77,000 |  |
| 5 | To build Member States’ SAA institutional capability to deliver support services and policies | 5.1. Strengthen Member States Capacity for Implementation of their respective LVCS | Capacity to implement strategies enhanced of 30 participants | Regional Workshop |  |  |  |  |  | Strengthens Member States Capacity | 25,000 |  | 25,000 |  | 50,000 |  |
|  |  | 5.2. Core Team, Triple Helix and SME Committee, Academia, RDS meeting | The regional Consultative Forum held | Regional workshop |  |  |  |  |  | The platform promotes regional and international collaboration among the key stakeholders – technology transfer, B2B among and others | 150,000 |  | 60,000 |  | 210,000 |  |
|  |  | 5.3. Strengthen SMEs capacity to respond to formal domestic and international orders | The designing and implementation of RDS, with a focus on trade and fashion trends designed and implemented | A project manager will be assigned on contract bases for the Regional Design Studio, the establishment of which was given to the Institute by COMESA Authority of Heads of States and Government (in its 19th Summit) as a Regional Flagship project focusing on SMEs incubation and development of skills, improved productivity and competitiveness to unlock the socio-economic potential of the Region’s leather sector. |  |  |  |  |  | This will assist in building the SME capacity of pattern making and also responding to customer requests. | 30,000 |  | 70,000 |  | 100,000 |  |
| Sub-Total (SO5) |  |  |  |  |  |  |  |  |  |  | 205,000 |  | 155,000 |  | 360,000 |  |
| 6 | Facilitate the development and implementation of occupational health and environmental management standards in the leather industry. | 6.1. Design a regional roadmap on occupational health and standards | Baseline survey on occupational health and standards management undertaken. | Mission |  |  |  |  |  | Occupational health and environment is important especially given the negativity associated with the leather sector on human healthy. These two aspects are becoming pillars of marketing in global premier markets and also for attracting green funds. | 5,000 |  | - |  | 5,000 |  |
|  |  |  | Baseline survey result (report) shared | Desk work |  |  |  |  |  |  | - |  | - |  | - |  |
|  |  | 6.2 Implement the occupational health standards management up graduation. | A technical and financial feasibility of implementing Occupational health and standards in selected tanneries undertaken | Mission |  |  |  |  |  |  | 5,000 |  | - |  | 5,000 |  |
|  |  |  | Work with selected tanneries in facilitating the upgrading of their facilities initiated; | Mission |  |  |  |  |  |  | 5,000 |  | - |  | 5,000 |  |
|  |  | 6.3.. Design a regional roadmap on effluent and environment management upgrading (Two Countries) | Regional roadmap on effluent and environment management upgrading designed | Desk work |  |  |  |  |  |  | 1,000 |  | 5,000 |  | 6,000 |  |
|  |  | 6.4. Validation and launch of the regional roadmap on effluent and environment management | Roadmap validated and launched | Workshop |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Total (SO6) |  |  |  |  |  |  |  |  |  |  | 16,000 |  | 5,000 |  | 21,000 |  |
| 7 | Facilitate investment and resource Mobilization for ALLPI and the leather sector | 7.1. Develop strong relationship with development partner | Meeting with development partner to increase ALLPI’s fund raising and Networking capacity conducted and project proposal developed | Desk Work/holding sideline meetings with development partners during different missions |  |  |  |  |  | Access to finance and linkages with investment and business Development Partners are key to upgrading and competitiveness of the leather industry in the African Continent. |  |  |  |  |  |  |
|  |  |  | ALLPI experts participated in regional & global forums | Attend International meeting and Workshop |  |  |  |  |  |  | 38,000 |  | 20,000 |  | 58,000 |  |
|  |  |  | Fundraise for hosting IULTCS Congress 2021 and World Leather Congress 2021 | Mission, Desk Works and preparation of promotional materials |  |  |  |  |  |  | 40,000 |  | 80,000 |  | 130,000 |  |
| Sub-Total (SO7) |  |  |  |  |  |  |  |  |  |  | 78,000 |  | 100,000 |  | 178,000 |  |
| 8 | To promote Export of value-added leather products | 8.1. Design a regional framework for promoting the export of value-added products; | Regional framework for promoting the export of value-added products designed. | Desk work |  |  |  |  |  | Export promotion is fundamental in the development of the leather sector and economies of member states | - |  | - |  | - |  |
|  |  | 8.2. Hold a regional workshop to facilitate the validation and domestication of the framework | Regional workshop to facilitate the validation and domestication of the framework held | Workshop |  |  |  |  |  |  | 10,000 |  | 20,000.00 |  | 30,000.00 |  |
|  |  | 8.3. Create strategic linkages with national and international export promotion institutions | Strategic linkages with national, regional, continental and international export promotion institutions established | Desk Work |  |  |  |  |  | Strategic linkages with international organization will contribute to enhance capacity for ALLPI staff and also resource mobilization to support the development of leather enterprises. | - |  | - |  | - |  |
|  |  |  | Intra and inter trade assessment to identify growing markets undertake | Desk Work |  |  |  |  |  |  | - |  | - |  | - |  |
|  |  | 8.4. Undertake intra and inter trade assessment to identify growing markets; | Intra and inter trade assessment undertaken to identify growing markets; | Desk Work |  |  |  |  |  | This will inform and contribute to market targeting the enterprises in the COMESA region. | - |  | - |  | - |  |
|  |  | 8.5. Design and implement activities aimed at entering the identified markets; | Activities aimed at entering into the identified markets designed and implemented | Desk Work |  |  |  |  |  |  | - |  | - |  | - |  |
|  |  | 8.6. Design a suitable curriculum to strengthen the capacity of enterprises to participate in regional, continental and international markets | A suitable curriculum designed to strengthen the capacity of enterprises to participate in regional, continental and international markets | Deskwork and Mission |  |  |  |  |  | Enterprises in the region has limited capacity to participate in regional, continental markets, hence there is a need to build their capacity. | 10,000 |  | 15,000 |  | 25,000 |  |
|  |  | 8.7 Design an M & E sub –framework which captures the activities of this objective. | M & E sub –framework which captures the activities of this objectives designed | Desk Work |  |  |  |  |  | Establishing monitoring and evaluation framework in the region | - |  | - |  | - |  |
|  |  | 8.8 Encourage and monitor the observance of Regional, Continental and International standards and specifications by the footwear and leather goods exporters | - Exporters become aware and adhere to Regional, Continental and International standards and specifications (to be started by 2020 and continuous activity. | Desk work ans sharing of standards and specifications |  |  | √ | √ |  | Facilitates access to regional and international markets | - |  | - |  | - |  |
|  |  | 8.9 Facilitate participations in different regional, continental and global leather and leather related trade fairs; Organize and sponsor potential buyers- seller meetings during trade fairs and other national, regional and international events | Market linkages, partnerships and knowledge transfer achieved. | Desk Work |  |  |  |  |  | To promote export |  |  |  |  |  |  |
|  |  | 8.10 Promote the establishment of e- commerce | E commerce system established By 2022 | Desk Work |  |  |  |  |  | This is in line with the ministerial meeting and aimed at prompting trade growth. | - |  | - |  | - |  |
|  |  | 8.11 Arrange Intra Africa (Continental) and international trade missions and support visits of entrepreneurs | Specific geographical markets for specific products identified, Partnerships and knowledge transfer achieved. (to be started by 2020 and continuous activity) | Desk Work for identification and advising of entrepreneurs for trade missions |  |  |  |  |  | Intra Trade Promotion | 2,000 |  | - |  | 2,000 |  |
| Sub-Total (SO8) |  |  |  |  |  |  |  |  |  |  | 22,000 |  | 35,000 |  | 57,000 |  |
| 9 | To enhance inclusiveness (includes participation of women, youth, and physically challenged) in the leather sector | 9.1 Design a Develop regional and continental framework for building inclusiveness in the designing and implementation of interventions in the leather sector; | A regional and continental framework for building inclusiveness in the designing and implementation of interventions in the leather sector developed | Desk Work |  |  |  |  |  | Inclusively is important in promoting the meeting of SDGs. | - |  | - |  | - |  |
|  |  | 9.2 Undertake an assessment on the participation of women, youth and physically challenged persons in the leather sector; | An assessment on the participation of women, youth and physically challenged persons in the leather sector undertaken | Desk Work |  |  |  |  |  |  | - |  | - |  | - |  |
|  |  | 9.3. Design and implement specific activities which are biased to promote the participation of the listed groups. | Specific activities which are biased to promote the participation of women, youth and physically challenged person designed and implemented. | Mission |  |  |  |  |  |  | 2,000 |  | 15,000 |  | 17,000 |  |
|  |  | 9.4. Design and implement an M & E sub –framework which captures the activities of this objective. | M & E sub –framework which captures the activities of this objective designed and implemented | Desk Work |  |  |  |  |  | Impact Assessment | - |  | - |  | - |  |
| Sub-Total (SO9) |  |  |  |  |  |  |  |  |  |  | 2,000 |  | 15,000 |  | 17,000 |  |
|  |  |  |  |  |  |  |  |  |  |  | 679,820 |  | 605,500 |  | 1,285.320 |  |

Proposed Budget for 2020

5.	The 2020 Draft Budget of the Leather and Leather Products Institute   indicated in Table 3 covers: Regular and Developmental Budgets and Table 4 Capital Budget for this Committee consideration.

6.	The Budget will be covered by the Assessed Contributions of Member States. The details of the ALLPI 2020 Assessed Contribution by Member States for Regular Budget is presented under Table 2.

Table 2: ALLPI 2020 Assessed Contribution of Member States

| Countries | 2019 Assed Contribution | Ration 2020 | 2020 Assessed Contribution | Note |
| --- | --- | --- | --- | --- |
| Burundi | 34,682.08 | 2.1 | 37,683.60 |  |
| Eritrea | 56,482.25 | 3.42 | 61,370.43 |  |
| Ethiopia | 313,790.28 | 19 | 340,946.83 |  |
| Kenya | 313,790.28 | 19 | 340,946.83 |  |
| Malawi | 59,455.00 | 3.6 | 64,600.45 |  |
| Rwanda | 122,213.06 | 7.4 | 132,789.82 |  |
| Sudan | 297,275.01 | 18 | 323,002.26 |  |
| Uganda | 130,801.00 | 7.92 | 142,120.99 |  |
| Zambia | 161,189.11 | 9.76 | 175,139.00 |  |
| Zimbabwe | 161,849.73 | 9.8 | 175,856.79 |  |
| Total | 1,651,527.81 | 100 | 1,794,457.00 | 7.97 |

7.	The Budget for 2020 amounts to a total of COM$ 2,480,432 of which COM$ 1,114,637,  COM$ 679,820 COM$ 80,475 and COM$ 605,500 are, respectively, Regular Budget and Strategic, Developmental Budget, Capital Budget  and Unsecured budget. The unsecured amount is to be mobilized from Developmental Partners and Consultancy service Professional fee.  The detailed budget lines and corresponding amounts are presented in Table 3 as follows:

Table 3:   ALLPI 2020 DRAFT BUDGET

| Item | 2018 |  |  | 2019 |  |  | Proposed Budget for the year 2020 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved Budget US$ | Actual Outrun to 31st December US$ | Variance US$ | Approved Budget US$ | Actual Outrun to 31st December US$ | Variance US$ | Proposed Budget US$ | Increase/ Decrease US$ | Variance % | Note |
| Expenditures |  |  |  |  |  |  |  |  |  |  |
| Basic Salary, Professional | 267,790.00 | 267,669.83 | 0.00 | 289,709.16 | 113,401.36 | 176,307.80 | 328,973.65 | 39,264.49 | 13.55 | 1 |
| Basic Salary IC, GS and Estate Staff | 96,300.00 | 93,948.05 | 2,351.95 | 119,784.60 | 57,591.78 | 62,192.82 | 132,094.40 | 12,309.80 | 9.32 | 2 |
| Housing Allowance | 119,100.00 | 117,524.99 | 1,575.01 | 153,519.14 | 61,454.53 | 92,064.61 | 160,325.00 | 6,805.86 | 4.25 | 2 |
| Dependency Allowance | 7,540.00 | 6,559.35 | 980.65 | 9,898.98 | 7,478.50 | 2,420.48 | 11947.00 | 2,048.02 | 17.14 | 1 |
| Spouse Allowances | 415.00 | 413.04 | 1.96 | 420.00 | 275.20 | 144.80 | 1,270.00 | 850.00 | 202.38 | 3 |
| Medical Expenses | 24,400.00 | 10,928.00 | 13,472.00 | 25,285.93 | 8,055.27 | 17,230.66 | 25,659.85 | 373.92 | 1.48 | 3 |
| Educational Expenses | 22,950.00 | 16,189.92 | 6,760.08 | 30,000.00 | 7,186.74 | 22,813.26 | 32,500.00 | 2,500.00 | 8.33 | 3 |
| Gratuity | 44,400.00 | 44,147.98 | 252.02 | 53,530.00 | 21,042.12 | 32,487.88 | 58,605.30 | 5075.3 | 8.8.66 | 1 |
| Provident Fund Management | 250.00 | 104.87 | 145.13 | 350.00 | 32.17 | 317.83 | 350.00 | 0.00 | 0.00 |  |
| Over time | 4,890.00 | 4,501.70 | 388.30 | 5,918.00 | 2,056.29 | 3,861.71 | 3,918.00 | -2,000.00 | -33.80 | 4 |
| Casual Worker | 2,700.00 | 1,012.96 | 1,687.04 | 4,000.00 | 2,334.57 | 1,665.43 | 4,000.00 | 0.00 | 0.00 |  |
| Temporary Employment | 15,628.00 | 0.00 | 15,628.00 | 15,778.00 | - | 15,778.00 | 0.00 | -15,778.00 | -100.00 | 5 |
| Recruitment Expenses (P) |  |  |  |  |  |  | 12,000 | 12,000.00 | 0.00 | 6 |
| Hospitality | 4,500.00 | 3,989.66 | 510.34 | 7,000.00 | 678.84 | 6,321.16 | 7,000.00 | 0.00 | 0.00 |  |
| Publication & Publicity and Subscription fee | 12,700.00 | 11,097.22 | 1,602.78 | 11,000.00 | 117.85 | 10,882.15 | 11,000.00 | 0.00 | 0.00 |  |
| Provision for legal issues |  |  |  | 4,000.00 |  | 4,000.00 | 4,000.00 | 0.00 | 0.00 |  |
| Office Supplies | 6,000.00 | 5,278.84 | 721.16 | 6,500.00 | 1,873.75 | 4,626.25 | 6,500.00 | 0.00 | 0.00 | 7 |
| Provision for External Audit Fees | 7,000.00 | 7,000.00 | 0.00 | 22,000.00 | - | 22,000.00 | 10,000.00 | -12,000.00 | -54.55 | 4 |
| Group Life Insurance | 12,000.00 | 10,645.52 | 1,354.48 | 20,000.00 | 4,772.20 | 15,227.80 | 25,000.00 | 5,000.00 | 25.00 | 7 |
| Motor Vehicle Fuel | 6,600.00 | 5,367.44 | 1,232.56 | 9,000.00 | 3,916.02 | 5,083.98 | 8,000.00 | -1,000.00 | -11.11 | 4 |
| Motor Vehicle Maintenance | 6,500.00 | 6,297.52 | 202.48 | 9,500.00 | 2,890.18 | 6,609.82 | 8,300.00 | -1,200.00 | -12.63 | 4 |
| Motor Vehicle Insurance | 3,000.00 | 2,941.53 | 58.47 | 3,500.00 | 1,251.92 | 2,248.08 | 3,500.00 | 0.00 | 0.00 |  |
| Furn. & Eqpt. Maintenance | 2,700.00 | 2,676.36 | 23.64 | 4,200.00 |  | 4,200.00 | 4,200.00 | 0.00 | 0.00 |  |
| Computer Maintenance | 500.00 | 72.32 | 427.68 | 500.00 | 396.61 | 103.39 | 500.00 | 0.00 | 0.00 |  |
| Communication Expenses | 15,000.00 | 15,000.00 | 0.00 | 18,500.00 | 2,848.00 | 15,652.00 | 23,000.00 | 4,500.00 | 24.32 | 8 |
| Miscellaneous Expenses | 5,000.00 | 4,463.14 | 536.86 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 9 |
| Office Maintenance and Security Expenses | 14,650.00 | 10,440.03 | 4,209.97 | 22,500.00 | 9,386.00 | 13,114.00 | 20,000.00 | -2,500.00 | -11.11 | 10 |
| Electricity and Water Charges | 2,100.00 | 690.74 | 1,409.26 | 3,500.00 | 534.44 | 2,965.56 | 3,500.00 | 0.00 | 0.00 |  |
| Cleaning Materials | 1,500.00 | 994.09 | 505.91 | 2,000.00 | 623.35 | 1,376.65 | 2,000.00 | 0.00 | 0.00 |  |
| Safety Cloth and Uniform | 2,400.00 | 1,369.46 | 1,030.54 | 2,794.00 | 0.00 | 2,794.00 | 3,794.00 | 1,000.00 | 35.79 | 11 |
| Translation | 7,560.00 | 7,489.94 | 70.06 | 7,000.00 | 0.00 | 7,000.00 | 7,500.00 | 500.00 | 7.14 | 12 |
| Insurance, Other Assets | 300.00 | 209.13 | 90.87 | 600 | 217.49 | 382.51 | 300.00 | -300.00 | -50.00 | 4 |
| Finance Charge | 4,600.00 | 3,860.35 | 739.65 | 5,500.00 | 1,600.70 | 3,899.30 | 5,500.00 | 0.00 | 0.00 |  |
| Sub-total | 720,973.00 | 662,883.98 | 58,089.02 | 867,787.81 | 312,015.88 | 555,771.93 | 925,237.20 | 57,449.39 | 6.21 |  |
| Strategic Activities |  |  |  |  |  |  |  |  |  |  |
| Annual Management Retreat Meeting and Consultation Committee Meeting | 88,500.00 | 96,365.14 | -7,865.14 | 70,000.00 | 13,126.00 | 56,874.00 | 60,000 | (10,000) | (14.29) | 13 |
| Board Meetings | 34,100.00 | 34,075.25 | 24.75 | 38,000.00 | 19,406.89 | 18,593.11 | 38,000 | - | - |  |
| Travel Expenses Officials | 46,800.00 | 46,771.89 | 28.11 | 46,400.00 | 5,809.81 | 40,590.19 | 46,400 | - | - |  |
| Training/Trade Fair/ Workshop/Seminar | 68,920.00 | 68,888.36 | 31.64 | 68,020.00 | 4,156.01 | 63,863.99 | 45,000 | (23,020) | (33.84) | 13 |
| Sub-total | 238,320.00 | 246,100.64 | -7,780.64 | 222,420.00 | 42,498.71 | 179,921.29 | 189,400 | (33,020) | (14.85) |  |

| Developmental Strategic Activities Draft Budget for the year 2019 | ALLPI Secured USD | Unsecured USD | Total USD | Note |
| --- | --- | --- | --- | --- |
| Strategic Objectives 1 (SO1) - To enhance ALLPI capacity to share best practices and strengthen value chain networks. | 229,820 | 155,500 | 385,320 | 14 |
| Strategic Objectives 2 (SO2) - To enhance value addition through Clusters/Incubators/ Service Centers development; | 35,000 | 40,000 | 75,000.00 | 14 |
| Strategic Objectives 3 (SO3) - To facilitate and promote the strengthening of the continental leather value chain; | 50,000 | 65,000 | 115,000.00 | 14 |
| Strategic Objectives 4 (SO4) - To build and operationalize a comprehensive production and trade database for the leather sector | 42,000 | 35,000 | 77,000.00 | 14 |
| Strategic Objectives 5 (SO5) - To build Member States’ SAA institutional capability to deliver support services and policies | 205,000 | 155,000 | 360,000 | 14 |
| Strategic Objectives 6 (SO6)- Facilitate the Development and Implementation of Occupational health and environmental management standards in the leather industry; | 16,000 | 5,000 | 21,000.00 | 14 |
| Strategic Objectives 7 (SO7) - Facilitate investment and resource Mobilization for ALLPI and the leather sector | 78,000 | 100,000 | 178,000.00 | 14 |
| Strategic Objectives 8 (SO8) - To promote Export of value-added leather products; | 22,000 | 35,000 | 57,000.00 | 14 |
| Strategic Objectives 9 (SO9) - To enhance inclusiveness (includes participation of women, youth, and physically challenged) in the leather sector. | 2,000 | 15,000 | 17,000.00 | 14 |
| Sub-total | 679,820 | 605,500 | 1,285,320 |  |
| Total | 1,794,457 |  |  |  |

Table 4:    Capital Budget

|  | USD | Note |
| --- | --- | --- |
| Office Computer and Printer (Cannon Printer 2520) | 6,275 | 13 |
| Office Furniture | 3,200 | 14 |
| Generator Stand By BHP 20, 17KVA, | 21,000 | 15 |
| Major Maintenance (Finishing) | 50,000 | 16 |
| Sub-total | 80,475 |  |

Note:

- This is based on the 35th Board of Directors’ decision, because of Professional positions upgrades.

- To secure the Institute’s, one additional Security Guard to be recruited and one Cleaner to replace the previous Cleaner who has moved to the store as a Clerk Staff and to align the IC salary scale with the other similar Institutions.

- Provision to cover the cost of the newly recruited Professional Staff.

- This is based on previous year’s utilization.

- This budget is not utilized (2019) because it is not sufficient to get qualified Bi-Lingual receptionist and currently the main Building is not functioning so that no place for receptionist.

- Provision for recruitment of two professional posts:

  - Programme Coordinator has resigned by his own so that the vacant position should be filled by next year.

  - Based on the 34th Board of Directors decision regarding recruitment of the Investment, Trade and Marketing position which was filled by Secondment from Ethiopia and now, it should be normalize the position.

- To cover insurance of the staff not from the host country.

- This budget line has been increased because of the volume of work and price escalation.

- This budget line has been cancelled by the Sub-Committee recommendation.

- It has already been requested for Major Office maintenance (No.18).

- This is because of additional expense for providing uniforms for Drivers.

- To cover the cost of translation of report documents into French and Arabic.

- Some of the activities moved to Developmental Strategic Activities.

- 2020 Work Programme.

- There is only one printer in the Institute and due to the fact that it has gradually been overloaded it has frequently failed and challenged the Institute’s activities. Therefore, this budget is held to replace the printer.

- To replace old furniture with poor conditions.

- The Institute’s standby generator is very old and has frequently failed; causing tremendous maintenance costs and the last two years the frequency of electricity blackout has increased. This has hampered the Institute to smoothly carry out its activities. Since it is badly necessary to replace this generator, the amount indicated is held as a budget for procurement of a new one.

- The Institute’s office building requires major maintenance so that all the staff have to move out of it till the maintenance work is completed. Accordingly, temporary offices have been constructed of a container and the staff have moved to these offices. The previous budget has partially been used for the construction of the temporary offices and the rest of it will be used for maintaining the building. So, it is necessary to hold the budget indicated here for completion of the maintenance work up to finishing stage.

Recommendations

The Africa Leather and Leather Products Institute hereby presents its 2020 Draft Work Programme and  Budget amounting to COM$ 1,874,932, the breakdowns of which are Regular (Recurrent and Strategic Activities) (COM$ 1,114,637)), Developmental (COM$ 679,820) and Capital (COM$ 80,475) Budget, to the Sub-Committee for consideration and forwarding to higher COMESA Policy Organs for the Council’s approval.