## WP2019
COMESA RIA WORK PLAN 2020
PROGRAMME | EXPECTED OUTCOME(S) | 2020 Expected Outputs | 2020 Planned Activities | SOURCE OF FUNDING |  |  | IMPLEMENTATION SCHEDULE
|  |  |  | RIA | MS | ICP | 1ST | 2ND | 3RD | 4TH
Capacity Building | Enhanced capacity of COMESA IPAs' officials in promoting, attracting and retaining Foreign Direct Investments (FDI) | An exchange and share successful investment promotion strategies and experiences between COMESA Member States in the higher objective of encouraging regional integration through performing as member of COMESA bloc rather than as a national IPA only. | Development of an online Knowledge Management Center (KMC) to allow NIPAs exchange updated information, best practices and experiences (based on the availability of funding) | × |  |  | √ | √ | √ | √
|  |  | organization of a retreat to COMESA RIA Board to brain-storm on the upcoming RIA Strategi Medium-Term Plan (based on the availability of funding) | × |  |  |  |  | √ | √
|  |  | Organise experience sharing, peer-to-peer learning, and networking event for COMESA IPAs aims at sharing successful practices and lessons learnt from a selected list of COMESA IPAs on different stages of investment promotion and facilitation (based on availability of funding) | × |  |  | √ | √
|  | Acquire updated information on best practices in investment promotion, facilitation services and strategy development | Organization of Research, online marketing, market intelligence and investor targeting training workshops for 1 Member State NIPA (based on the approval of the proposal submitted to 11th EDF project) |  |  | × | √ | √ | √ | √
|  |  | Organization of investment facilitation best practices training workshops for 1 Member State NIPA (based on the approval of the proposal submitted to 11th EDF project) |  |  |  | √ | √
|  |  | Development of an Investor Tracking System (ITS) for 1 Member State NIPA (based on the approval of the proposal submitted to 11th EDF project) |  |  |  | √ | √
|  |  | Kick off the implementation of regional media and communication campaign for COMESA region (based on the approval of the proposal submitted to 11th EDF project) |  |  |  | √ | √
|  |  | Organization a series of training workshops for Burundi Investment Promotion Agency (API) on the development of Investment Promotion Strategies and cluster-based FDI prromotion (based on approval of proposal submitted to cooperating partners) |  |  | × | √ | √ | √ | √
|  |  | Organization a series of training workshops for Burundi Investment Promotion Agency (API) on the development of proactive aftercare strategies (based on approval of proposal submitted to cooperating partners) |  |  | × | √ | √ | √ | √
|  |  | Development of proactive investment promotion and aftercare strategy for Burundi Investment Promotion Agency (API) (based on approval of proposal submitted to cooperating partners) |  |  | × | √ | √
|  |  | Development of an Investor Tracking System (ITS) for Burundi Investment Promotion Agency (API) (based on approval of proposal submitted to cooperating partners) |  |  | × |  |  | √ | √
|  |  | Development and implementation of an image builidng and country visibility campaign for Burundi (based on approval of proposal submitted to cooperating partners) |  |  | × | √ | √ | √ | √
|  |  | Development of two sectoral studies and printed promotional materials for Burundi Investment Promotion Agency (API) (based on approval of proposal submitted to cooperating partners) |  |  | × | √ | √
|  |  | Organization a series of training workshops for Eswatini Investment Promotion Agency (EIPA) on the development of Investment Promotion Strategies and cluster-based FDI prromotion (based on approval of proposal submitted to RISM) |  |  | × | √ | √
|  |  | Organization a series of training workshops for Eswatini Investment Promotion Agency (EIPA) on the development of proactive aftercare strategies (based on approval of proposal submitted to RISM) |  |  | × | √ | √
|  |  | Development of proactive investment promotion and aftercare strategy for Eswatini Investment Promotion Agency (EIPA) (based on approval of proposal submitted to RISM) |  |  | × | √ | √
Investment Promotion | Increase Foreign Direct Investment (FDI) and trade inflows to COMESA region | Enhanced awareness of business/investment environment and opportunities in COMESA region and its individual Member States amongst regional and international business community and FDI stakeholders as a favourable investment destination in Africa | Facilitate the participation of COMESA Member States in conferences targeting the promotion of investment environment and opportunities in Africa. |  | × | × | √ | √ | √ | √
|  |  | Promotion of business, trade and investment related events in COMESA Member States through RIA's online portal and other social media channels. | × |  |  | √ | √ | √ | √
|  |  | Implementation of 1 inward/outward investment promotion missions targeting European investors based on approval of COMESA proposal to 11th EDF and availability of funding) |  |  | × | √ | √ | √ | √
|  |  | Implementation of an international media campaign to promote COMESA region as an attractive investment destination, as well as COMESA Secretariat and institutions mandates, services and acheivements (based on the availability of funding) | × |  |  | √ | √ | √ | √
|  | Enhancing COMESA RIA's regional and international business network | Participate and speak at business/ investment stakeholder events or seminars | × |  |  | √ | √ | √ | √
|  |  | Avail speaking opportunities for COMESA Member NIPAs at regional and international investment forums | × |  |  | √ | √ | √ | √
|  |  | COMESA RIA re-branding; change COMESA RIA's logo and implementation of a marketing and communication campaign to brand the new logo | × |  |  | √ | √ | √ | √
|  |  | Development and excution of investor outreach campaign for COMESA Member States (based on the availability of funding) |  |  | × | √ | √ | √ | √
|  | Encourage intra-regional trade, investment flows, and cooperation | Implementation of 1 intra-regional fact-finding/investment promotion missions (based on the availability of funding) |  | × |  |  | √ | √
Information Collection and Dessimination | FDI stakeholders are aware of business environmennt and opportunities in COMESA Member States individually and COMESA region collectively | Updated COMESA RIA publications and promotional materials | Update and print COMESA Investment Teaser 2020 | × |  |  |  | √ | √
|  |  | Development of COMESA Investment Report 2020 in cooperation with COMESA Industry and Agriculture Division and COMESA Statistics Unit | × |  |  |  |  | √
Development of a pubication highlighting COMESA Member States' efforts and progress made in Ease of Doing Business indicators over the years
|  |  | Update 1 or 2 Practical Guides for COMESA Member States | × |  |  | √ | √ | √
|  |  | Development of quarterly Newsletters to be published and distributed amongst regional and international FDI stakeholders including targeted investors, IPAs, chambers of commerce, business associations, media channels, etc.) | × |  |  | √ | √ | √ | √
|  |  | Development of sector profiles/studies including regional value chains (based on the availability of funding) |  |  | × | √ | √ | √ | √
|  | Acting as an information hub for business and investment related Information (studies, news, opportunities, etc.) for regional and international business stakeholders | Continuous update of COMESA RIA online portal and social media channels (twitter, LinkedIn, etc.) with positive news and success stories, Member States' events, and COMESA Secretariat and RIA's activities. In addition to publishing RIA's publications, brochures, and studies on partners' online channels and business libraries. | × |  |  | √ | √ | √ | √
Notes: MS: Member State ICP: International Cooperating Partners